Report of the PTWS Task Team on Exercises

Meetings, 2-4 March 2011

Meeting 1:  2:00-3:30 pm, Wednesday, 2 March 2011

Meeting 2:  4:30-5:30 pm, Thursday 3 March 2011

Meeting 3:  1:30-3:00 pm, Friday 4 March 2011

Co-Chairs Laura Kong (ITIC), Jo Guard (New Zealand)

Introduction:

The PTWS WG2 Task Team on PTWS Exercises met for three brief sessions during the PTWS Working Group 2 Meeting in Wellington, New Zealand 28 February – 4 March 2011. The Co-Chairs are Jo Guard (New Zealand) and Laura Kong (ITIC).  Dr. Kong chaired the meetings due to absence of Ms. Guard who was deployed to Christchurch to assist in the earthquake response to the 22 February 2011 earthquake.  Members of the Task Team are PTWC, JMA, New Zealand (GNS Nora Gale, Ken Gledhill, MCDEM, David Coetzee), Samoa (Filomena Nelson), Papua New Guinea (Mathew Moihoi), Russia (Tanya Ivelskaya, Sakhalin TWC), Philippines (PHIVOLCS), Nicaragua (INETER, Angelica Munoz), France (Dominique Reymond), Indonesia (BMKG), a representative from South America, and the PTWS Secretariat.  The Task Team’s Terms of Reference (ICG/PTWS-XXIII.2) are to review the PacWave08 Summary Report to identify lessons learned, and design and carry out PacWave11.  The IOC should announce the Exercise to Member States 180 days in advance and the Exercise Manual should be available at least 90 days in advance.

The two previous PTWS exercises, Exercise Pacific Wave 2006 (PacWave06, http://itic.ioc-unesco.org/index.php?option=com_content&view=article&id=1658&Itemid=2333&lang=en) and 2008 (PacWave08, http://itic.ioc-unesco.org/index.php?option=com_content&view=article&id=1597&Itemid=2333&lang=en) were the 1st basin-wide exercises conducted under the coordination of UNESCO/IOC.  PacWave06 became the model for other basin-wide exercises, such as Indian Ocean Wave 2009 and Caribbean Wave 2011.  Due to the 2009 Samoa and 2010 Chile Tsunamis, the biannual Pacific-wide exercise has been delayed.  The PTWS Steering Committee recommended in its meeting in August 2010 to have the next exercise, Exercise Pacific Wave 2011 (PacWave11), in first half of November 2011 as a multi-scenario, real-time exercise to enable all PTWS countries to participate.

PacWave06 and PacWave08:

Dr. Kong summarized the previous Pacific-wide exercises, including its objectives, format, conduct, scenarios, post-exercise assessments, findings and outcomes, and recommendations.

Several common outcomes were the need to

- Continually review and update TWFPs;

- Emphasize stakeholder coordination as a key to effective warning;

- Have written warning and response SOPs, especially at local levels, to enable fast orderly response; and

- Identify and resolve the continuing communication challenges (lack of reliable infrastructure) in reaching geographically remote islands and regions in a timely manner.

Nonetheless, exercises were considered extremely valuable for strengthening preparedness and increasing awareness.  The last important recommendation from PacWave08 identified the high value of both actual exercise component (warning receipt, notification, and response) and the post-exercise evaluation component that assesses the SOPs’ performance and identifies problems and where possible, immediately takes corrective actions.  It was noted that the compilation of post-exercise responses was labor-intensive and contained a great range of responses making it difficult to easily cross-compare the 2006 and 2008 exercise in detail.

She opened the floor for further discussion on lessons learned from PacWave08.  She additionally asked for input on what the objectives and goals of PacWave11 should be, in light of the three deadly local tsunamis in the last three years in the Pacific.

As few had recently read the PacWave08 Summary Report, the discussion was deferred and will be solicited from Task Team members through email.  Similarly, for PacWave11 objectives.  Additionally, the Co-Chairs will soliciy input from the PTWS SC and at the PTWC-JMA Tsunami Warning Coordination meeting.  This will be included in the PTWS Exercises Task Team report ICG/PTWS-XXIV.

She reported that at the TOWS Inter-ICG Task Team meeting in December 2010, it was noted that there is no generic and consistent guideline available for ICGs on the development, management, and evaluation of tsunami exercises.  With the prevalence of exercises now being conducted, the Task Team recommended that a compilation be done noting that the focus of exercises is on the testing of SOPs of TWCs and DMOs; such a resource could be shared across ICGs and be applicable to both exercise coordinators and exercise players (watch & warning centres, as well as disaster management agencies).

PacWave11 Planning

PacWave11 Dates:

The Group discussed the feasibility of designing and conducting a multi-scenario exercise and agreed that PacWave11 will be carried out on 9-10 November 2011. It was noted that this would be during or just prior to APEC, which will be held in Honolulu this year.  PacWave11 will thus offer a high-visibility opportunity to showcase the PTWS system.  Many APEC high-level diplomats will be in Hawaii for APEC.  APEC Countries should take advantage of this timing to improve tsunami awareness and build the case for increased sustainable resources.

Announcement:

IOC Circular Letter announcing PacWave11 should be issued by 9 May 2011 (180 days in advance).  The PTWS Secretariat would need the draft letter by 1 May 2011.

The PacWave11 Exercise Manual should be made available by 9 August 2011 (90 days in advance).

Scenario Location and Magnitude:

The Group identified the following scenario locations.  Task Team members from each of these regions should be consulted for the locations.

- NW Pacific – Kamchatka.   Noting that PacWave08 was off-northern Japan and so further sources are probably not necessary.

- South China Sea

  - Manila Trench

  - Sulawesi Sea (forecast pts would need to be added) – request from Malaysia

- West Pacific - Philippines Trench

- SW Pacific

  - Tonga Trench.  Note that his was the original source requested by PTWS-XXIII (2009).

  - Vanuatu

- South America – Southern or Northern Chile, Southern Peru – this scenario could take advantage of NZ 2010 Tangaroa National Exercise since coastal and DART measurements, and other info and inject had already been completed by NZ.  The TT representative from South American should be consulted.

- Central America – Nicaragua

- North Pacific - Aleutians Islands, noting the Shumagin Gap could be the source location.

The earthquake magnitude that triggers the destructive tsunami will be based on the length of the associated subducting trench.

In order to identify the best PacWave11 scenarios from among the choices above, PTWC will compute scenarios with its RIFT model and share the results.  ITIC will provide an online PacWave11 Scenarios survey to the PTWS TT, PTWS WG2, and the PTWS Steering Committee in order to solicit input on which scenarios are the highest priority to exercise.  This Survey will be ideally conducted before the PTWC-JMA Coordination Meeting so that it can be discussed and final scenarios chosen.

Conduct:

To reduce confusion of many messages from many scenarios, and to reduce the size of the manual and save on costs for hard copy printing and distribution., it was decided that exercise messages should be available and accessed online through a secure web site.  Participants would be able to access their chosen scenario and the ensuing messages and associated data in a user-friendly manner.

Time of Event:

The request from the SW Pacific is for the events to commence during daytime working hours.

The Task Team will seek inquire to other regions if there are similar requests.

International Tsunami Warning Centre Messages

Because each event will likely be a destructive basin-wide event, messages could continue for 24 hours.  Because of this, and knowing that there will be multi-scenarios, only the beginning messages would be transmitted, and ensuing messages would be issued only periodically.  These issued would include the initial earthquake information, any revised earthquake parameters, expected tsunami wave arrivals and forecasts, and sea level observations.

However, all messages will be available in the PacWave11 Exercise Manual and online through a secure site.

During the exercise, there will be lot of messages and it could get confusing.  There is a trade-off work-wise for PacWave11 – there could be a lot of scenarios with fewer messages, or fewer scenarios with more messages.  PTWC and JMA will review the different types of messaging arrangements (time start, how many msgs to issue, and when, etc) to decide on the most feasible during the planned April 11-13, 2011 PTWC-JMA Tsunami Warning Coordination Meeting in Honolulu.

Enhanced new tsunami warning products should be implemented and tested in PacWave11

JMA reported that it could only provide NWPTAC messages for only 1 scenario in the NWPTAC area of responsibility.

Post-Exercise Evaluation:

The Chair noted that a large activity of the Task Team is in the post-exercise analysis to assess the success of PacWave11; since compilation and analysis of country-submitted post-exercise surveys by hand can be time-consuming and tedious, it was agreed to employ electronic surveys if possible to facilitate a more-efficient and faster evaluation process.

It was suggested to use and modify electronic evaluation tools used by NZ 2010 Tangaroa national exercise for PacWave11

To encourage consistency and build commonality in approach among ICGs and if ready, it was proposed to encourage IOWave11 to use the same methodology and/or questionnaire developed by the PTWS for PacWave11.   PTWS Exercises Co-Chairs will liaise with IOWave11 (to be held 12 Oct 2011) Task Team Chairs India and Australia. Chris Ryan, Australia BOM, volunteered to serve as contact for interfacing.

PacWave 11 Preparations –Actions, Responsibilities, Dates

- Aim – to be finalized

- Objectives – to be finalized

- Scenarios Finalization

- RIFT models completed – March 11 - PTWC

- Survey TT and WG2 – March 14-18 - ITIC

- Survey issuance was delayed until 8 April 2011, due to the 11 March 2011 tsunami.

- PTWC-JMA Tsunami Warning Coordination and Exercise Pacific Wave 2011 Planning Meeting,  11-13 April 2011.  This self-funded meeting will coordinate the proposal to ICG/PTWS-XXIV on enhanced new PTWS products.  SW Pacific WG and South China Sea WG Chairs will attend, as well as Indonesia.

Day 3 will coordinate PacWave11.  NZ will attend and continue working with ITIC 13-20 April 2011 for PacWave11.

- Exercise Date Announcement by IOC – 9 May 2011 (at least 180 days) – draft letter 1 May 2011 to PTWS Technical Secretary – Co-Chairs will draft (after previous exercises) and circulate to TT members for comment.

- Exercise Manual Finalization – 9 August 2011

But the sooner the better so can be briefed and used in any trainings May-Sept

  - General (Co-Chairs, ITIC)

  - Messages (PTWC/WCATWC, JMA)

  - Press release templates (Co-Chairs/ITIC to review past and adjust as needed),

  - Evaluation process/questionnaire (Co-Chairs/ITIC) – Review past questionnaire and propose new process); PNG Mathew Moihoi to help and provide comment, but feedback also from TT.

  - Circulate to TT for comment and improvement

- Exercise Conduct and Post-Exercise Evaluation guidance – improve upon previous to allow for better cross-comparison of evaluations – NZ, ITIC and provide as soon as possible

- PacWave11 Marketing and Training - information briefings and/or SOP training – 3rd quarter 2011.  Countries should form PacWave11 Planning Committees to identify who, what, and how exercise will be conducted within their country.  Where possible and requested, briefings and SOP training could be requested, pending funding.

- PacWave11 Press Release - at least 1 week prior to PacWave11 – IOC internationally and countries nationally.  Note that PacWave11 will occur during APEC 2011 - US could provide a press release as part of its Hawaii hosting of APEC (US NOAA Ed Young/ITIC/PTWC to inquire)

- PacWave11– 9-10 Nov 2011

- Exercise Evaluations - due 9 Feb 2012 (within 90 days) – will use electronic reporting as described in Exercise Manual

- Summary Report (MCDEM, ITIC, Task Team, Filomena Nelson, maybe Australia and others) – due for reporting at the IOC Assembly, June 2012

Task Team on PTWS Exercises  (Rec ICG/PTWS-XXIII.2 PTWS Exercises)

Terms of Reference:

(i)	Review the PACWAVE08 evaluation report

(ii)	Identify lessons learned and develop recommendations based on the PACWAVE08 evaluation and submit recommendations to the PTWS Steering Committee

(iii)	Design and carry out a third end-to-end Pacific-wide exercise with the following characteristics:

a.	The exercise will take place preferably in the fourth quarter of 2010

b.	The exercise scenario be a major tsunami originating in the central south Pacific (e.g., Tonga-Kermadec) to complement previous scenarios in other places

c.	The exercise date be finalized by the Task Team and the exercise announced to Member States at least 180 days in advance of the exercise date

d.	The exercise manual including instructions to Member States regarding their participation and the evaluation instrument be prepared with content and structure similar to what was prepared for the previous two Pacific-wide exercises, but taking into account lessons learned and any need to collect additional information

e.	The exercise manual be distributed to Member States at least 90 days in advance of the exercise date

f.	Participating Member States be asked to complete and return the evaluation instrument no more than 90 days following the exercise

g.	The exercise be played out in real time

h.	The exercise be considered as a way to test new products from the international TWCs including graphical products