## Slide 1
Guideline Overview:
How to Plan, Conduct, and Evaluate Tsunami Exercises
Exercise Guidance Brief
September 2011
Laura Kong, UNESCO/IOC-NOAA ITIC
Jo Guard, MCDEM, NZ
Notes: <number>

## Slide 2: How to Plan, Conduct, and Evaluate Tsunami Exercises
NZ Ministry of Civil Defense and Emergency Management
ITIC
July 2011
July 28, 2026
<number>
Notes: Primary resource: Commission oceanographique intergouvernementale. How to Plan, Conduct and Evaluate Tsunami Exercise. IOC Technical Series No. xx. Paris, UNESCO, 2011 (English)
<number>

## Slide 3: Exercise Philosophy
Goal: Improve overall readiness and mitigate effects of natural disasters
Any exercise should be a part of a master plan
  Overall strategy (national /agency)
    Subordinate strategies
  Established policies, laws, regulations
  Supported by training, exercise, and evaluation
July 28, 2026
<number>
Notes: <number>

## Slide 4: Exercise Cycle
Analyze Need
Evaluate Exercise
Conduct Exercise
Design Exercise
July 28, 2026
<number>
Notes: Animated. Click after each box—arrow and next box appears. Click after last box to loop around.
<number>

## Slide 5: Types of Exercises
Discussion/Presentation
Field/Operations
Orientation
Tabletop
Drill
Functional
Full-Scale
Planning & Preparation
Time & Resources
Training Value
Complexity
July 28, 2026
<number>
Notes: Table 1 "How to Plan" and HSEEP V1 Ch2
<number>

## Slide 6: Components of an Exercise
Determine NEED and SCOPE
Establish exercise PLANNING TEAMS
Establish TIMELINES and MEETINGS
Define exercise AIM and OBJECTIVES
Define KEY PERFORMANCE INDICATORS
Define EVALUATION procedures
Develop the SCENARIO
Develop MASTER SCHEDULE OF EVENTS
CONDUCT EXERCISE
EVALUATE EXERCISE
ENABLE IMPROVEMENTS
July 28, 2026
<number>

## Slide 7: Needs Assessment
Review current plans
  Hazards, risks, vulnerabilities
  What needs practice?
  What are your priorities?
Review past exercises
  When? Who? What learned?
  What improvements made?
Identify available resources
  Budget and resources
  Limitations
July 28, 2026
<number>
Notes: <number>

## Slide 8: Needs Assessment (cont)
Assessment should identify key issues for consideration in preparation for and development of the exercise
  Hazards, untested improvements, weaknesses
  New equipment, personnel, facilities
  Budget and resources
  Coordination with other agencies (internal/external)
See checklist
July 28, 2026
<number>
Notes: <number>

## Slide 9: Types of Exercises
Orientation
Drill
Tabletop
Functional Exercise
Full-Scale Exercise
Any of these (or combination) could be used by individual nations or agencies during IOC Wave Exercies to test internal/external procedures
July 28, 2026
<number>
Notes: <number>

## Slide 10: Orientation
  Familarization; "Walk through"
  No previous training or exercise
  Review new personnel, procedures, facilities, SOPs
  Review new risks and mitigation
  Orientation for new leadership
  Example: set up a mock welfare center and walk staff and leadership through how the center is organized
July 28, 2026
<number>
Notes: <number>

## Slide 11: Drill
Exercise specific equipment or procedure
Test response time
Training
Verify resources
Example: activate an Emergency Operations Center or use alternate communications systems (radios, cell phones, etc.)
July 28, 2026
<number>
Notes: <number>

## Slide 12: Tabletop Exercise
AKA "Discussion Exercise" or "DISCEX"
Moderator controlled
Used to practice problem solving and coordination without time pressures
Promotes familiarity with plans, examines staffing contingencies, coordination, information sharing, and training
Example: Discuss response to tsunami threat with only message injects from warning centers
July 28, 2026
<number>
Notes: <number>

## Slide 13: Functional Exercise
AKA "Operational" or "Tactical" exercise
Complex response/multiple agencies
Without people "on the ground"
Exercise control group
Measure resources, assess preparedness, assess inter-jurisdictional relations
Example: Multi-agency response requiring evacuation of costal area
July 28, 2026
<number>
Notes: <number>

## Slide 14: Full-Scale Exercise
AKA "Practical" or "Field" exercise
Includes on the ground response to simulated situation
Simple (single agency) or complex (multi-agency)
Tests all aspects of warning and emergency management systems and processes
Example: Post-tsunami response w/ volunteer "victims" using real rescue equipment and crews
July 28, 2026
<number>
Notes: <number>

## Slide 15: Example - Training, Exercise, and Evaluation Schedule
Training, Exercise, and Evaluation Schedule 20XX |  |  |  |  |  |  |  |  |  |  |  | 
Agency | 1st Qtr |  |  | 2nd Qtr |  |  | 3rd Qtr |  |  | 4th Qtr |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Agency 1 |  | Drill |  |  | Functional |  |  | Functional |  | Full scale |  | 
Agency 2 | Tabletop |  | Drill |  | Drill |  | Functional |  |  |  |  | 
Agency 3 |  | Seminar |  | Tabletop |  | Drill |  | Tabletop |  | Drill |  | 
Agency 4 | Seminar |  | Seminar |  | Tabletop |  | Tabletop |  | Drill |  | Drill | 
 | Communications |  | Warning Center |  | First Responders |  |  |  |  |  |  | 
July 28, 2026
<number>
Notes: <number>

## Slide 16: Internal Exercises for PacWave11
July 28, 2026
<number>
Notes: Consider: each country/agency identify what type(s) of exercises(s) they will be conducting.
Each type of exercise has an overhead cost in people, time, and resources.
<number>

## Slide 17: Designing an Exercise
Define the operations
Identify the stakeholders
Identify hazards and risks involved
Define the geographical target area
Establish the degree of realism
Set date and time
Determine the Scope
July 28, 2026
<number>
Notes: See chart p. 18
<number>

## Slide 18: Designing an Exercise
Task Team
Planning Team
Control Staff
Exercise Director
Evaluation Team
External Agencies (as required)
Establish Exercise Planning Teams
July 28, 2026
<number>
Notes: <number>

## Slide 19
Task Team Responsibilities
Planning
Conduct
Exercise narrative
Master Schedule of Events List (MSEL)
Messages and injects
Post-exercise evolutions
Summary report
July 28, 2026
<number>
Establish Exercise Planning Teams
Notes: <number>

## Slide 20
In-Country Exercise Planning Team Responsibilities
  Develop IOC Wave Exercise to own requirements
  Include representatives from major agencies
  Are not exercise players
  Could be Exercise Director/Evaluator w/in own country/agency
  Planning teams down to lowest level of community involvement
In-Country Planning Teams
July 28, 2026
<number>
Establish Exercise Planning Teams
Notes: <number>

## Slide 21
General Exercise Roles
  Members
    IOC Wave Task Team
    In-Country Planning Team Members
  Control Staff Roles
    Exercise Director
    Observers - Evaluators
    Agency Representatives
Exercise
Control Staff
July 28, 2026
<number>
Establish Exercise Planning Teams
Notes: <number>

## Slide 22
Control Staff Responsibilities
  Manage in-country input to exercise
  Facilitate progress of exercise scenario
  Represent notional representatives
  Control/coordinate role players
  Provide corrective advice
  Follow risk management strategies
  Monitor MSEL
Exercise
Control Staff (cont)
Establish Exercise Planning Teams
July 28, 2026
<number>
Notes: <number>

## Slide 23
Overall Exercise Director
  Chair of Tsunami Wave Task Team
  Lead International Warning Center(s) (i.e., RTSPs, PTWC, etc)
In-country National Director
  Supervises flow of exercise
  Monitor MSEL
  Adjusts for unanticipated events
  Maintain order and professionalism
  Assists production of end of exercise report
Exercise
Control Staff (cont)
Establish Exercise Planning Teams
July 28, 2026
<number>
Notes: <number>

## Slide 24
Evaluation Team
  Evaluates objectives against KPIs
  Observes/assess processes, procedures, techniques
  Evaluate and report on meeting objectives
  Evaluate effectiveness of exercise facilitation
  Provide input to exercise debrief
Exercise
Control Staff (cont)
Establish Exercise Planning Teams
July 28, 2026
<number>
Notes: <number>

## Slide 25
External Agencies
  POC for agency
  Provides advice/input for their agency
  Enter issues into scenario/provide control documents
  Ensure input is consistent with other agencies and aims/objectives of the exercise
  Respond to requests from exercise participants
Exercise
Control Staff (cont)
Establish Exercise Planning Teams
July 28, 2026
<number>
Notes: <number>

## Slide 26: Designing an Exercise
Timeline
  Establishes timeframe for milestone events
  Select exercise date then work backward
Regular Meetings
  Geographic spread can limit face-to-face
  Utilize email, VTC, websites
  Have agenda and follow it
  Concept and objectives, initial planning, mid-term planning, and final planning conferences
EstablishTimelines and Meetings
July 28, 2026
<number>
Notes: <number>

## Slide 27: Designing an Exercise
Milestones
(See page 23)
Milestone / Description
1 Member State Tsunami National Contact (TNC) and Tsunami Warning Focal Point (TWFP) receives IOC Circular Letter announcing the exercise
2 TWFP responds to the contacts specified in the IOC Circular Letter advising the name and contact details of his/her country’s National Tsunami Wave exercise contact.
3 TWFP / TNC disseminates the IOC Circular Letter to in-country agency representatives
4 TWFP establishes an in-country National Exercise Planning Team including key stakeholder agencies. Provincial or Local Planning Teams may be established as necessary.
5 In-country national planning teams select a scenario out of the Tsunami Wave set of scenarios (if more than one scenario is provided)
6 In-country National Exercise Planning Teams plan the exercise (use the How to Plan, Conduct and Evaluate Tsunami Wave Exercises Guideline)
7 In-country planning teams receive and read the Exercise Tsunami Wave Exercise Manual
8 In-country planning teams receive and read applicable documents such as the International TWC Operational User Guide and other related information (for example, for Exercise Pacific Wave 2011, these are the PTWS Operational Users Guide and the PTWC Experimental Products guideline)
9 In-country National Exercise Planning team checks the Tsunami Wave website for updates, Guideline, and other documentation
10 Conduct the Tsunami Wave exercise
11 National Exercise Planning Team coordinates, and as appropriate, conducts and collates in-country debriefs
12 In-country agencies complete Tsunami Wave evaluation (Word version, or online electronic version) forms at local and provincial levels then forward to the in-country National Exercise Planning Team
13 National Exercise Planning Team collates evaluation forms and completes the national evaluation online. (Note: only one online evaluation to be completed per country).
14 National online evaluations are collated and summarized by the Tsunami Wave Exercise Task Team who produce a final exercise report.
July 28, 2026
<number>
Notes: <number>

## Slide 28: Designing an Exercise
Meetings
(See pages 26-27)
July 28, 2026
<number>
Notes: <number>

## Slide 29: Designing an Exercise
July 28, 2026
<number>
Meetings
(See pages 26-27)
Notes: <number>

## Slide 30: Designing an Exercise
Milestones Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
2011 |  |  |  |  |  |  |  |  |  |  |  | 2012 |  |  | 
13-Summary Rpt
10-PW11
Exercise
8-Develop and Conduct Training
1-Establish Aim
-Establish Objectives
-Decide on Scope
11-Complete Evaluations
July 28, 2026
<number>
6-Publish Exercise
Guide
8-Develop and Conduct Training (In-country)
4-Announcement
Letter
3-Dev Scenarios
5-Dev Exercise Manual
-Dev Users Guide
-Dev Evaluation Form
12-Exercise Team
-Steering Committee
-Experimental Products Team
Meetings
Events
Documents
Meetings
Blue--IOC/ITIC
Green--Country teams
Purple--Agencies
9-Press Release
Notes: <number>

## Slide 31: Designing an Exercise
Broad statement of intent
Provides direction for exercise
Only one aim
  Subordinates may establish additional aims
  Should complement the higher level aim
  Example: To improve local and regional source tsunami warning capability in the Pacific/Indian Ocean / Caribbean / Mediterranea
Establish Exercise Aim
July 28, 2026
<number>
Notes: <number>

## Slide 32: Designing an Exercise
"What is to be done?" (in terms of results)
Who does what, under what conditions, according to what standards
Developed by Exercise Task Team
More specific and performance-based than exercise "aim"
What participants will work towards, evaluate, or observe
Establish Exercise Objectives
July 28, 2026
<number>
Notes: <number>

## Slide 33: Designing an Exercise
Small exercise = few objectives
Large exercise = hundreds of objectives
Recommends about 10 per agency
  Countries/agencies should develop additional internal objectives
  Internal objectives should link to exercise objectives
Objectives are starting point for the evaluation process
July 28, 2026
<number>
Establish Exercise Objectives (cont)
Notes: <number>

## Slide 34: Designing an Exercise
Should be clear, concise, performance-focused
  Action in observable terms
  Conditions under which action to be performed
  Standards/levels of performance
July 28, 2026
<number>
Establish Exercise Objectives (cont)
Notes: <number>

## Slide 35: Designing an Exercise
Guidelines for writing SMART objectives
Specific
Measurable
Achievable
Realistic
Task Oriented or Time Driven
July 28, 2026
<number>
Establish Exercise Objectives (cont)
Notes: <number>

## Slide 36: Establish Exercise Objectives
SMART Objectives (see page 30)
July 28, 2026
<number>
Notes: <number>

## Slide 37: Designing an Exercise
Key Performance Indicators (KPIs)
  Define and measure progress towards an objective
  May further define an objective
  Helpful when formulating evaluation tools and measurements
  Examples: The information issued by our national decision-making and dissemination point was timely.
  Arrangements to assemble the in-country disaster management group were in place before the exercise.
Determine Key Performance Indicators
July 28, 2026
<number>
Notes: <number>

## Slide 38: Establish Exercise Objectives
Workshop to develop internal objectives
  Review macro objectives (i.e., PacWave11, IOWave11)
  Identify micro objectives (i.e., agency, country, locality, etc.)
Cross-walk objectives vertically and horizontally (higher authority, adjacent agencies)
Ensure objectives support exercise aim
Develop Objectives Workshop
July 28, 2026
<number>
Notes: <number>

## Slide 39: Exercise Evaluation
Exercise requirements must be defined
During design phase formulate:
  Evaluation instructions
  Evaluation tool
  Evaluation forms
Evaluation looks for actions that determine if objectives and Key Performance Indicators (KPIs) are met
July 28, 2026
<number>
Notes: <number>

## Slide 40: Exercise Evaluation
Describes events up to start of exercise
  Captures attention and motivates participants
  Provides informationneeded during exercise
Assists writing Master Schedule of Events List (MSEL)
Country/Agency refines scenario for theri specific purpose
  May include effects beyond impact area
  Timeline for restoration of lifeline utilities
Develop Scenario
July 28, 2026
<number>
Notes: <number>

## Slide 41: Exercise Evaluation
Announce exercise well in advance for participant preparation
  Date of exercise
  Exercise aim
  Scenerio(s)
  Conduct of the exercise
  Additional information sources
Publish exercise manual 90 days in advance
Exercise Manual
July 28, 2026
<number>
Notes: <number>

## Slide 42: Exercise Documentation
Announcement letter
Exercise manual
Master Schedule of Events List (MSEL)
Evaluation guidelines and forms
Points of contact
Corrective action plans
Exercise summary reports and evaluations
Findings and recommendations
July 28, 2026
<number>
Notes: Complete list on p. 36
<number>

## Slide 43: Exercise Evaluation
Manual provides detailed information
  Exercise overview
  Scenerio details
  How exercise will be conducted
  Master Schedule of Events List (MSEL)
  Products to be issued
  Post-exercise evaluation method
Distribute to all relevant representatives
Exercise Manual (cont)
July 28, 2026
<number>
Notes: <number>

## Slide 44: Exercise Evaluation
Determine participants
Encourage participants to invite subordinate/ adjacent agenties/reps to participate
Determine level of support
  Full
  Partial
  Facilitation
  Not engaged
Confirm Participation
July 28, 2026
<number>
Notes: <number>

## Slide 45: Exercise Evaluation
Levels of Participation
July 28, 2026
<number>
Notes: See chart p. 35
<number>

## Slide 46: Exercise Documentation
Exercise purpose
Exercise aim
Exercise objectives and KPIs
Exercise scope
Exercise appointments
Methods of communication
Public information strategies
Evaluation strategy
Observer program
Budget and expenditure
July 28, 2026
<number>
General Instruction
Issued after exercise manual is published--contains:
Notes: <number>

## Slide 47: Exercise Conduct
Purpose: to generate a response
Communicate developments for participants
May be a single message/inject or a series
Listed in MSEL
Communicated in various manner:
  Telephone (landline, satellite, cellular, text)
  Radio broadcast
  Fax, email, written note, in person discussion
Use most realistic method
Use standard format
July 28, 2026
<number>
Messages and Injects
Notes: <number>

## Slide 48: Exercise Documentation
July 28, 2026
<number>
Message and Inject Preparation
Step | Action
1 | Identify an expected action.
2 | Determine WHO should send the message and WHAT is stated to motivate the expected action.
3 | WHO would realistically send the message? HOW will the message be transmitted? WHAT information does the message contain (everything needed to make a decision)? WHO is the intended recipient the message?
4 | Keep the message REALISTIC.
5 | PRACTICE the message before release. Does it motivate the expected action?
6 | Ensure the message is numbered and has a time ofrelease. (Possible done in conjunction with the MSEL.)
Notes: <number>

## Slide 49
Participants may not respond as expected
  Anticipate and plan for possible differences
  Exercise Director will decide appropriate response
  Response must be realistic
May identify "knowledge gaps" for further review
July 28, 2026
<number>
Spontaneous Messages
Exercise Conduct
Notes: <number>

## Slide 50: Master Schedule of Events List (MSEL)
Detailed sequence of events that "runs" the exercise
MSEL only distributed to exercise control staff
DO NOT distribute to exercise participants
MSEL identifies events linked to tsunami products, messages, and injects
July 28, 2026
<number>
Notes: Complete list on p. 36
<number>

## Slide 51: MSEL
Contents
Serial number
Day/date
Time
Activity of event
Location
Desired outcome
Control documents
Comments/remarks
Initiator
July 28, 2026
<number>
Format
(Required Items)
Spreadsheet format containing:
Notes: Complete list on p. 40
<number>

## Slide 52: MSEL
Recipient
Resources
Role Players
Monitoring and follow- up arrangements
Critical completion times
Cross referencing
Links with the objective
Expected actions
July 28, 2026
<number>
Format
(Optional Items)
See example in Annex IV
Notes: Complete list on p. 40
<number>

## Slide 53: MSEL
Keep exercise moving at steady pace
Problems closer to scene scheduled before those more distant
Communication problems may create lack of information from reporting agencies
Recovery/repair efforts will take considerable time to arrange
July 28, 2026
<number>
Timing of Events
Notes: <number>

## Slide 54: MSEL
Large exercises require a lot of detail
  Cross walk references for facts and data
  Check frequency and distribution of exercise items
Provide all events with a serial number
Retain data in sortable database/spreadsheet
  Helps evaluation/after-action process
  Shows time dimension of actions
July 28, 2026
<number>
Control of Events
Notes: <number>

## Slide 55: Exercise Setup
Larger the exercise the more setup required
  See checklist p. 42-43
Facilities
  Should use same facilities as normal operations
  Control staff needs separate room/facility
  Control room needs extra radios, fax, computers, display boards etc.
July 28, 2026
<number>
Notes: Complete list on p. 42
<number>

## Slide 56: Exercise Setup
Training prior to exercise
  Exercise aims and objectives
  Scenario(s)
  Participants roles
  Evaluator roles/responsibilities
Provide evaluators with necessary materials
  Exercise documents and evaluation materials (tools/forms)
  Relevant plans, procedures, agreements
  Provide copy of MSEL but keep close hold
July 28, 2026
<number>
Evaluator Training
Notes: <number>

## Slide 57: Exercise Setup
Training includes what to look for, what to record, how to use tools
  Evaluator must know designated positions/times
  Observe action but do not get involved
  Focus on what is relevant
  Legible notes, including time
  Remain in assigned position
  Answer participant questions without prompting
    Ask questions if necessary
    Do not "lead" participants
July 28, 2026
<number>
Evaluator Training (cont)
Notes: <number>

## Slide 58: Exercise Setup
Exercises attract visitors from agencies/countries not actually involved in the exercise
Structured/organized agenda
  Provides overview of exercise
  All visitors need proper identification/access
  Need point of contact at each site/location
  Include tour of exercise area if possible
May require accommodation/transportation support
July 28, 2026
<number>
Observer Program
Notes: <number>

## Slide 59: Exercise Setup
May be real or simulated
Media extremely important in tsunami awareness/preparation
Ensure local media is aware of exercise well before start date
Communication plan should identify response to media
Example announcements
July 28, 2026
<number>
Media
Notes: <number>

## Slide 60: Conduct the Exercise
Seek/provide exercise briefings to appropriate audiences
  Exercise planners and participants
  Decision makers (all levels down to village/tribal)
  New staff
International Exercise Tsunami Wave Task Team can provide
Multiple means to communicate: planning meetings, newsletters, site visits, etc.
Final briefing prior to exercise start
July 28, 2026
<number>
Notes: <number>

## Slide 61: Conduct the Exercise
Initial exercise briefing
  Time and duration
  Exercise boundaries
  Locations of key venues/activities
  Expected outcomes
  Safety briefing
  Exercise logistics
Identify procedures in event a real event occurs during the exercise
July 28, 2026
<number>
Exercise Briefings
Notes: <number>

## Slide 62: Conduct the Exercise
Provided to control staff only after initial briefing
  Roles and responsibilities
  Exercise documents
  Methods
  Departures from scripts
  Responding of participant actions
  Notekeeping fordebrief
Commence exercise after control staff briefing
July 28, 2026
<number>
Exercise Briefing
Control Staff
Notes: <number>

## Slide 63: Conduct the Exercise
Lead country evaluator meet with exercise coordinator
  Verify roles and responsibilities
  Obtain updates/changes to scenario
  Summarize MSEL--identify important events
    Many events occuring--need to know most important
    Ensures proper evaluation
Tour exercise site if possible
July 28, 2026
<number>
Exercise Briefing
Evaluators
Notes: <number>

## Slide 64: Control the Exercise
Start after last briefing and when control staff in place
  Schedule briefing to match scenrio
  Release "Exercise Start Message"
Exercise Director uses MSEL to control exercise
  Rectify problems and keep exercise flowing
  Modify flow to ensure objectives are met
Tsunami bulletins/products introduced per MSEL
Allow spontaneity--generate experience
July 28, 2026
<number>
Notes: <number>

## Slide 65: Control the Exercise
Rate of injects depends on participants response
Reaction may not be expected--examine consequences
"Free play" needs to be controlled
  Should not have negative effect on exercise
  In-country/agency rep may need to intervene
Control staff monitor MSEL actions
July 28, 2026
<number>
Sustaining & Controlling Activity
Notes: <number>

## Slide 66: Control the Exercise
Participant frustration may cause backlog or conflict between players
  May require exercise director intervention
  May require pause in exercise
  Goal: positive experience for all
Communication channels will slow or stop
  Prevent public from distracting operations staff
  Public info/media plan is essential
  Public access lines may overload
July 28, 2026
<number>
Sustaining & Controlling Activity (cont)
Notes: <number>

## Slide 67: Control the Exercise
Slow down pace of exercise
  Reschedule events/allow more reaction time
  Discard unimportant injects
Speed up pace of exercise
  Accelerate delivery of injects
  Keep supply of optional injects ready
  Add secondary events
  Add planning event requiring group activity
  Add misdirected injects
July 28, 2026
<number>
Sustaining & Controlling Activity (cont)
Notes: <number>

## Slide 68: Control the Exercise
Relieve overload
  Reassign injects to alternate agency
  Thin the injects
    Essential to exercise
    Nice to have (time and resources permitting)
July 28, 2026
<number>
Sustaining & Controlling Activity (cont)
Notes: <number>

## Slide 69: Control the Exercise
End of exercise
  A controlled activity
  Pre-determined time by Exercise Director
  Announce with end of exercise message
  Immediate hot debrief
  Account for all personnel before dismissal
July 28, 2026
<number>
Sustaining & Controlling Activity (cont)
Notes: <number>

## Slide 70: Exercise Evaluation
Purpose
  Identify improvements
  Determine if objectives were achieved
Key evaluation points:
  Does staff have written SOP to follow?
  Does staff have templates/pre-scripted communication to speed and standardize comm?
  Were stakeholders educated on their roles, expectations, and required/expected actions?
Evaluation through debriefing
Validation through investigation of activity
July 28, 2026
<number>
Notes: <number>

## Slide 71: Exercise Evaluation
Debriefing moderated by trained facilitator
  What went right/wrong--without blame
  Note specific questions that arose
  Acknowledge good performance
  Seek constructive criticism--focus on improvements
  Record information for later reports
  Summarise key points
  Identify follow-up actions
July 28, 2026
<number>
Debriefing
Notes: <number>

## Slide 72: Exercise Evaluation
Hot debrief
  Conduct immediately after end of exercise
  Initial feedback from Exercise Director
  Round-table feedback from participants
  Evaluator feedback
  Provide proper acknowledgements
July 28, 2026
<number>
Debriefing (cont)
Notes: <number>

## Slide 73: Exercise Evaluation
Cold debrief (w/in four weeks after exercise)
  What happened?
  What went well?
  What needs improvement?
  What plans/procedures/training need amendment?
  What follow-up required?
  Was exercise realistic?
  How could exercise be improved?
Focus on exercise effectiveness
July 28, 2026
<number>
Debriefing (cont)
Notes: <number>

## Slide 74: Exercise Evaluation
Planning team, control team, evaluator debrief
  Conduct as soon as possible after exercise
  Collects observations/thoughts about exercise
  Leads to preliminary analysis of exercise
July 28, 2026
<number>
Debriefing (cont)
Notes: <number>

## Slide 75: Exercise Evaluation
Items for evaluators to consider (p. 53)
July 28, 2026
<number>
Debriefing (cont)
Notes: <number>

## Slide 76: Exercise Evaluation
Compares performance vs. expected actions
Did the exercise:
  Address identified need?
  Provide opportunity to simulate actions of real emergency?
  Lead to improvements in policies, plans, prodecures, or individual performance?
July 28, 2026
<number>
Validation
Notes: <number>

## Slide 77: Exercise Evaluation
Validation conducted by:
  Observation of performance
  Evaluation forms
  Debrief notes
  Interviews
  Post exercise questionnaires
Outcome may be retested in future exercise
July 28, 2026
<number>
Validation
Notes: <number>

## Slide 78: Exercise Evaluation
Describes what happened
Describes best practices and strengths
Identifies areas for improvement
Provides recomendations
Provides collated summary for country evaluations
July 28, 2026
<number>
End of Exercise Report
Notes: <number>

## Slide 79: Exercise Evaluation
Recomendations from exercise report must be acted on
Each country/agency should:
  Assign responsibility for each action item
  Monitor progress of change recommendations
  Report progress to senior officials
  Return equipment
  Settle payments of accounts
  Provide letters of appreciation as appropriate
July 28, 2026
<number>
Exercise Follow-up
Notes: <number>

## Slide 80: References
Commission oceanographique intergouvernementale. How to Plan, Conduct and Evaluate Tsunami Exercise. IOC Technical Series No. xx. Paris, UNESCO, 2011 (English).
Department of Homeland Security (2007). FEMA: Homeland Security Exercise and Evaluation Program, Vols 1-4 Feb 2007.
FEMA: Homeland Security Exercise and Evaluation Program. https://hseep.dhs.gov/pages/1001_HSEEP7.aspx (accessed 10 Jul 2011).
July 28, 2026
<number>
Notes: <number>

## Slide 81: www.pacwave.info Questions?
<number>
UNESCO/IOC-NOAA
International Tsunami Information Center
Jo Guard
Emergency Mgmt Advisor – National Operations
Ministry of Civil Defence & Emergency Management
The Department of Internal Affairs Te Tari Taiwhenua
Wellington, New Zealand
Tel: +64 4 495 6818
Fax: + 64 4 473 7369
Email: jo.guard@dia.govt.nz
Dr. Laura Kong
Director
UNESCO/IOC-NOAA International Tsunami Information Center
Honolulu, Hawaii USA
Tel: 1-808-532-6423
Fax: 1-808-532-5576
Email: laura.kong@noaa.gov
Notes: <number>