International Post-Tsunami Survey for the 27 February 2010 Chile Tsunami

International Tsunami Survey Team - Chile (ITST-Chile)

GUIDANCE

BACKGROUND, as of 9 March 2010

The 27 February 2010 magnitude 8.8 Chilean earthquake and tsunami caused damage and over 400 deaths in the coastal regions of central Chile. Following the earthquake, the US Tsunami Warning Centers issued a widespread tsunami warning as advice to countries throughout the Pacific; national authorities are then responsible for issuing warnings to their populations on the tsunami threat to their coasts.

Locally in Chile, lives were lost due to the tsunami in Pelluhue, Isla Orrego, Dichato, and on Robinson Crusoe Island located near the epicenter. The highest measured tsunami amplitude was 2.6 m on the Valparaiso, Chile sea level gauge; Talcahuano and Juan Fernandez gauges stopped working after the initial tsunami waves. The highest tsunami waves were 5 m high and reported by eyewitnesses on Robinson Crusoe Island. Around the Pacific, sea level gauges recorded tsunami waves of 0.5 to 1.5 m amplitude, and fortunately no lives were lost.

According to the National Geophysical Data Center (NGDC, http://www.ngdc.noaa.gov/hazard/) Global Historical Event databases, this is the largest instrumental earthquake observed in Chile since the 1960 magnitude 9.5 Valdivia earthquake and tsunami that killed over 1,200 people, including 60 deaths in Hawaii. Globally, this is the 6th largest instrumental earthquake and one of 280 deadly tsunamis. NGDC compiles data on significant earthquakes, volcanic eruptions, and tsunamis including socio-economic information such as deaths and damage.

ITST-CHILE SUMMARY

UNESCO’s Intergovernmental Oceanographic Commission is coordinating post-tsunami field surveys of the tsunami and its effects. It is doing so at the request of the Government of Chile (GoC). The coordination effort will be centered at UNESCO Santiago. The goals include:

- Promote sharing of data among field parties

- Minimize logistical problems for visitors and hosts

- Link visitors to Chilean collaborators

- Provide the GoC with a summary of the ITST-Chile findings •

The coordination for this effort will be handled by the International Tsunami Survey Team (ITST) - Chile Coordination Team (ICT). ICT members include scientists from UNESCO Santiago, Pontificia Universidad Catolica de Valparaiso (UCV), the Intergovernmental Oceanographic Commission in Paris (IOC), the U.S. Geological Survey (USGS), and the International Tsunami Information Centre (ITIC).

Toward these ends, UNESCO encourages all Survey Teams to stay in regular contact with ICT headquarters in Santiago.

Tsunami disasters attract a large number of local, national, international professionals to investigate scientific, economic, social impacts. Some of these data are perishable making it essential to collect quickly. Important data may also be desirable from locations that are logistically difficult to assess without local assistance and access. At the same time, Emergency Agencies are focusing on public safety, critical support lifelines and infrastructure, resource mobilization to meet its citizens immediate post-event emergency response needs. To carry out both efforts, coordination and cooperation is critical. If data from science teams are made available, it will immediately contribute to better-informed and ultimately, more practical and efficient response and recovery decision-making. Building from concepts employed in post-earthquake technical clearinghouses, the ITST-Chile will utilize a simplified implementation of a science/technical clearinghouse to provide an efficient framework for central coordination, information sharing and integration of the data collected from the 2010 Chile tsunami.

ITST-Chile will follow a format similar to the ITST-Samoa 2009, but modified to recognize that a complete survey needs to cover a much larger geographic area (Chile and Pacific). This will require more efficient and streamlined mechanisms for information sharing and coordination through secure electronic mediums that will be hosted by UNESCO/IOC – NOAA ITIC.

ITST-CHILE GUIDING PRINCIPLES

1. The Mission of the ITST-Chile is

- To understand the character of the tsunami and its impact in both the near-source and distant regions

- Provide information on the impacts to the GoC to enable it to enhance their tsunami disaster risk management practice

2. Logistics and Planning

- There will be an ITST-Chile Coordination Team to consist of UNESCO Santiago (Ricardo Norambuena, Chile coordination), Universidad Católica de Valparaiso (Dr. Marco Cisternas, Science coordination), UNESCO/IOC-NOAA ITIC (Dr. Laura Kong, overall) and US Geological Survey (Dr. Brian Atwater).

- • The ITST-Chile Coordination team will work with local and international scientists and government officials to enable a coordinated survey and to keep information flowing amongst Survey Teams with a goal of seeking to minimize overlap and duplication. Guidance for surveys in Chile will be based in part on the results of the Rapid Response Post-tsunami survey, conducted 8-20 March 2010. Team leads were Ricardo Norambuena (UNESCO-Santiago), Marcelo Lagos (Universidad Católica de Chile), Daniel Melnick (Chilean but at Postdam University), Marco Cisternas (Universidad Católica de Valparaiso)

- Transportation, Lodging: Survey Teams are responsible for their own transportation and lodging. UNESCO Santiago and local scientists may be able to assist if needed.

- Funding: UNESCO and IOC are unable to provide funding support to Survey Teams.

3. Tasks: The ITST-Chile should carry out the following tasks. Teams may focus on the collection of just one data type:

- Measure maximum tsunami inundation, flow depths, and maximum run-up; to the extent possible ‘walk the inundation’ line in order to collect an exact summary of the inundation of impacted communities.

- Collect geological samples of sediments left by the tsunami;

- Measure the type and severity of damage to different types of buildings and record what factors appeared to control damage levels;

- Collect and measure information about the environmental and biophysical system impacts of the tsunami;

- Collect information about survivor experiences and stories through interviews;

- Explore the human and community vulnerability and resilience factors at work in different places;

- Provide a map the above information in their summary

4. Survey Team Guidance and Logistics

- Each team shall make known its dates of travel and survey plan to ITST-Chile. ITST-Chile will make every effort to:

- Compile the main objectives of each Survey;

- Inform each Survey Team of activities done by other previous Surveys;

- Inform each Survey Team on the general situation and present conditions.

- For specific needs, assist to facilitate contacts, information, and other requests.

- Receive the general outcomes of each Survey in order to facilitate the next Surveys.

- It is requested that local scientists or other local organizations or volunteers be included with your international team wherever possible. This is to bridge any language or cultural sensitivities, as well as to build local science experience and capacity.

- Please review the IOC Post-Tsunami Survey Field Guide (IOC Manual and Guides 37, First Edition. 1998. 61 pp., English, French, Spanish, Russian) and conduct your surveys consistent with these objectives. ITIC will provide you with its Tsunami Questionnaire (English and Spanish) and Eyewitness Survey to guide your data collection work. You are encouraged to use them. As needed, these can be translated into languages other than English.

5.	Information Sharing and Reporting

Each Survey Team coordinated through ITST-Chile is requested submit to ITST-Chile within 4 weeks of concluding the Field Survey a one-page summary plus eventually pictures or maps, to be used for further guidance.

UNESCO is committed to preserve the data and intellectual property rights of the scientists who collect and interpret these important data. UNESCO also recognizes the high value of the data to governments for response and recovery planning, as well as for information sharing to enable better tsunami science understanding and so improve tsunami mitigation. To enable activities, UNESCO commits to the following:

- As ITST-Chile members are volunteers from organizations and research centers with related interests, participants should not lose the rights to publish data they collect. No data or outcomes from the Summary Report to GoC or data provided to other governments, will be released publicly for one year;

- At the conclusion and after quality-control by each Survey Team, the ITST-Chile Coordination Team will prepare a compilation Summary Report based on summaries received. The estimated delivery date of the report will be 4 months after the completion of ITST-Chile surveys. The Report will be shared with the GoC only.

- The ITIC will provide a secure ITST-Chile electronic method (Basecamp ITST-Chile) for data collectors to upload Survey metadata and data. The site will also contain Survey Team information, briefing reports, and other related information. Simple upload forms or spreadsheets will be provided to facilitate this process. Before and during fieldwork, Teams can upload daily Survey metadata so that everyone can keep track of progress and coverage, and in order to reduce duplication. ITIC will host a separate ITST-Chile Web site for general public viewing, and general document distribution.

ITST-Chile Coordination Team - Contact Information:

Ricardo Norambuena (Chile coordination and liaison)

Coordinador Programas Costeros

Enrique Del Piano 2058

Providencia, Santiago, CHILE

Tel. (56-2) 472 4619, (56-2) 472 4630

Mobile: +56 9 9219 64 92

Home. 56 (32) 212 34 07

E-mails: r.norambuena@unesco.org, r.norambu@gmail.com

Dr. Marco Cisternas (science liaison)

Escuela de Ciencias del Mar

Pontificia Universidad Católica de Valparaíso

Av. Altamirano 1480, Valparaíso, Chile

Casilla (P.O. Box) 1020, Valparaíso 1, CHILE

Teléfono (Phone): +56 (32) 2274261

E-mail: marco.cisternas@ucv.cl

Dr. Laura S. L. Kong (coordination, data/report liaison)

Director

UNESCO/IOC-NOAA International Tsunami Information Center

737 Bishop St., Ste. 2200

Honolulu, Hawaii 96813 USA

Tel: 1-808-532-6423

Mobile: 1-808-392-4415

Fax: 1-808-532-5576

E-mail: l.kong@unesco.org, laura.kong@noaa.gov

Bernardo Aliaga (IOC Tsunami Unit)

Technical Secretary for ICG/CARIBE EWS

Intergovernmental Oceanographic Commission/UNESCO

Tel: +33 (0) 1 45 68 39 80

E-mail: B.Aliaga@unesco.org

Dr. Brian Atwater (science liaison)

U.S. Geological Survey at Department of Earth and Space Sciences

University of Washington

Box 351310

Seattle, WA 98195-1310

Tel: 1-206-553-2927

Fax: 1- 206-553-8350

E-mail: atwater@usgs.gov

Dr. Costas  Synolakis

Professor of Civil and Environmental Engineering

Director, Tsunami Research Center

Viterbi School of Engineering

University of Southern California

Los Angeles, California 90089-2531

Tel: +1 213 740 5129

Mobile (US):   +1 213 820 8800

Mobile (Greece):  + 30 6932 357 593

FAX: +1 213 744 1426

E-mail:  costas@usc.edu

Dr. Sergio Barrientos (science liaison)

University of Chile

Tel:  56-2-978 4309 office

265 secretary

Mobile:  56-9-81997793

E-mail: sbarrien@dgf.uchile.cl