INTERGOVERNMENTAL OCEANOGRAPHIC COMMISSION

(of UNESCO)

PTWS Implementation Plan

version 2, 2010

# INTRODUCTION

This Implementation Plan (ImPlan) describes the current status of the PTWS and highlights the requirements and specifications for upgrading the existing Pacific Tsunami Warning System (PTWS).

The implementation of actions contained in this plan is the sole responsibility of Member States.  However, where resources are limited, Member States are encouraged to seek support through existing bilateral agreements and from other donors that can provide financial and technical support to achieve the deliverables.  The actions below comprise activities that Member States should integrate into their national development plan, annual implementation plan, and be part of the budgets of national and/or local agencies that have tsunami mitigation and warning responsibilities.

The implementation, improvement and upgrading of ocean-wide Tsunami Warning Systems (TWSs) is a complex on-going process involving Member States (MS) activities and commitments through their respective agencies and institutions as well as the active participation of international organizations.  Special mention deserves the need for involvement, ownership and commitment of local concerned communities through the organized civil society and local institutions including schools. ?Thus? this Implementation Plan is at the same time a reference document which provides guidelines and defines priorities, and a dynamic document, reflecting the current status of the PTWS upgrading at a given time. Updated versions of the Implementation Plan will be maintained at the Intergovernmental Oceanographic Commission (IOC) web site and distributed at ICG/PTWS sessions.

From its inception Pacific-wide Warning/Advisory provision services by the Pacific Tsunami Warning Centre in Hawaii (PTWC), the North-West Pacific Tsunami and Advisory Centre in Tokyo (NWPTAC) and the West Coast and Alaska Tsunami Warning Centre in Palmer, Alaska (WCATWC) have been stably and robustly operated with high reliability for more than 40 years.

Those centres have been making ceaseless efforts to improve their services by introducing new technologies as well as to maintain the operational systems.

Nonetheless national warning systems are still under construction. Exchanging observational data between neighbouring MSs (sometimes even within a single MS) or establishing national systems which are reliable during times of emergency are still pending challenges for several Member States.

Given the damage and huge number of casualties caused by the 2004 tsunami in the Indian Ocean the awareness of urgent necessity for preparing countermeasures against tsunami threats has been increasing.  There is still a need for more capacity building and disaster prevention education to achieve further and sufficient awareness.

As the budget for PTWS and all other TWSs in other oceans provided by the governing body, UNESCO/IOC, is by far insufficient to cover coordination and capacity building activities (e.g. through the International Tsunami Information Center ITIC) or even instrumentation and warning centre updates, the success of this Implementation Plan is strongly dependent on the active participation of MSs and their contributions either in kind or cash. However, where resources are limited, Member States are encouraged to seek support through existing bilateral agreements and from donors that can provide financial and technical support to achieve the deliverables. Additionally possible extra budgetary contributions by concerned organizations such as ISDR, UNDP or technical agencies such as AusAID, USAid, JICA, Cosude or DIPECHO etc. should be taken into account and factored in when appropriated.

A basic requirement for operating, maintaining and optimizing a TWS is adherence to a common data policy, the sharing of all information and products, and the agreement on common standards and guideline.

Tsunami warning systems to a large extent share resources with other early warning systems, and their responsible agencies. Therefore tsunami warning systems are “embedded” into a multi-hazard approach, and are increasingly addressing all ocean-related hazards.

Ideally this Implementation Plan as a living document should incorporate the views, action plans and the actual status and progress of action items of all the PTWS Working Groups, as far as they contribute to analyze and suggest modifications and upgrading of the existing warning system components.

- Framework for the global Working Group on Tsunamis and other Ocean Hazards Warning and Mitigation Systems (TOWS-WG)

The Pacific Tsunami Warning and Mitigation System operates as an important component within the global tsunami warning and other ocean-related hazards early warning systems.  The governance of PTWS is provided through an Intergovernmental Coordination Group (ICG), under the Intergovernmental Oceanographic Commission (IOC) of UNESCO.  The PTWS reflects the key principles of the Framework for the Global Tsunami and other Ocean-related Hazards Early Warning System (GOHWMS) as well as the subsequent activities and decisions of the TOWS-WG, which was established by IOC’s 41st Executive Council. The TOWS-WG has the task to harmonize regional ICG structures to create efficiency and facilitate exchange of knowledge and information among the ICGs. For PTWS and its officers this can be broken down into the following bullet points:

- Identifying warning and mitigation system requirements unique to the Pacific Ocean basin

- Capitalizing, to the extent practicable, on existing international groups with relevant responsibilities such as GLOSS and JCOMM

- Harmonising structure, standards, and practices among ICGs

- Integrating with other international systems and organizations such as WMO and ISDR

- Collaborate on research and development across ICGs

  - Strategic Pillars

Based on the GOHWMS framework and the respective task teams of the TOWS WG, the Pacific Tsunami Warning and Mitigation Systems Medium Term Strategy is comprised of three Pillars supported by three foundational elements.  The three Pillars are:

- Risk Assessment and Reduction: hazard and risk identification and risk reduction

- Detection, Warning and Dissemination: rapid detection and warning dissemination down to the last mile

- Awareness and Response: public education, emergency planning and response

The supporting foundational elements are:

	Interoperability: free, open and functional exchange of tsunami information

	Research: enhanced understanding and improved technologies and techniques

	Capacity Building: training and technology transfer

	Funding and Sustainability:  resources to sustain an effective PTWS

- Summary of Priority Actions

PI: Performance Indicator

BK: Benchmark

TBD: To be developed (by the Secretariat)

| Actions in Risk Assessment and Reduction | Perform Indicators | Benchmark |
| --- | --- | --- |
| 1. PTWS countries should complete their tsunami risk assessment taking into account existing information and data from other relevant studies. | Tsunami risk assessment report | By end of IP period, countries have completed at least 50% of this work |
| 2. PTWS countries should provide tsunami event data to the World Data Center in order to improve the global tsunami historical database | Increase in amount of data | By end of IP period, countries affected by a tsunami have submitted data to WDC |
| 3. PTWS countries should, or where applicable support, the update of existing or development of new tsunami inundation maps for vulnerable communities identified by risk assessment studies. | Inundation map | By end of IP period, at least 50% of countries with the need to have at least preliminary maps have maps in place. |
| 4. Provide opportunities for countries to build their capacity to be able to conduct their own risk assessments. Such training could include, but is not limited to, tsunami numerical modeling and production of inundation maps. Based on identified needs, priority should be given to trainees from countries located in Central America, South West Pacific and South East Pacific, and South China Sea. | Number of trainings and trainees trained | By end of IP period, 50% of countries listed have had at least 5 personnel trained. |
| 5. PTWS countries should continue to improve their tsunami hazard database through paleotsunami studies that can extend the historical tsunami record back in time, and with each tsunami, the conduct of post-tsunami field surveys to document the event. International collaboration to build national capabilities is encouraged. | Number of studies completed | By end of IP period about 30% to 50 % of given number requested studies completed |
| Actions in Detection, Warning, and Dissemination (ICG/PTWS WG 2) |  |  |
| 1. The Secretariat shall secure by the end of 2010 that all PTWS countries have formally defined their TWFP and TNC and/or reviewed and updated their TWFP and TNC details. TWFP information should be forwarded to PTWC, NWPTAC, and WC/ATWC. | Number of MSs that have submitted TWFP and TNC | Before ICG/PTWS-XXIV, all MSs have submitted TWFP and TNC information and/or updated contacts |
| 2. Detection: Address operational limitations of PTWS warning centers as indicated in the PTWS Operational Users Guide with specific focus on improving seismic data availability for monitoring and more quickly evaluating earthquakes, especially to be able warn against local tsunamis. Priority stations identified through sensitivity and gap analysis. | Increase in number of seismic stations | By end of IP period, 3 to 4 additional seismic stations are installed and operational within PTWS area of responsibility. |
| 3. Detection: Address operational limitations of PTWS warning centers as indicated in the PTWS Operational Users Guide with specific focus on improving seismic source characterization techniques to more quickly evaluate the tsunamigenic potential of large earthquakes. | Number of techniques available and applied | Time to analyze seismic data is shortened to how many minutes as compared to current timeframe? |
| 3. Detection: Address operational limitations of PTWS warning centers as indicated in the PTWS Operational Users Guide with specific focus on improving sea level data availability for monitoring and more quickly evaluating the tsunami threat. Priority stations identified through sensitivity and gap analysis. | Increase in number of stations | By end of IP period, 3 to 4 additional stations installed or upgraded, and operational within PTWS area of responsibility. |
| 4. Detection: 4.1 Work with TOWS to establish requirements for timely detection to support tsunami warnings. 4.2 Perform earthquake and tsunami detection sensitivity analysis to identify data gaps. Seek to reduce detection time and improve quality of source characterization so as to provide more timely and accurate forecasts. | Outcomes of meetings Number of sensitivity studies conducted | By end of IP period, provide input to TOWS; sensitivity analyses conducted for entire Pacific and its sub-regions |
| 5. Warning and dissemination: Enhance tsunami advisory products to improve their clarity, understanding and speed of dissemination, and to ensure consistency with products and terminology used globally. Reference Recommendation PTWS-XXIII.1 | Number of appropriate changes to enhance products | By end of IP period, tsunami products simplified and harmonized where appropriate |
| 6. Dissemination: In coordination with the PTWS Technical Secretariat, establish a reliable and secure mechanism for Member States to regularly review and update their TWFP and report to the IOC. (Reference Recommendation PTWS-XXIII.3). Implement similar or the same mechanism for use in the regular communication tests conducted by PTWC, NWPTAC, and WC/ATWC. | TWFP information available to countries | By end of IP period, TWFP review mechanism implemented, and used for communications test. |
| 7. Dissemination: Establish and recommend reliable mechanisms for Member States to receive information from the regional to the national tsunami warning centers, e.g. from PTWC, NWPTAC, and WC/ATWC to TWFPs according to recommendations in the PTWS Operational Users Guide. (Ref. Recommendation PTWS-XXIII.8). | Number of reliable mechanisms | By end of IP period, countries implemented at least 2 reliable mechanisms |
| 8. Dissemination: Identify and recommend the most reliable mechanisms of the available operational technologies for Member States to disseminate information from national authorities to the general public (Ref. Recommendation PTWS-XXIII.8) | Number of reliable mechanisms | By end of IP period, countries implemented at least 1 reliable mechanism |
| 9. Training: MS in collaboration with the Technical Secretariat, ITIC and other appropriate regional organizations provide opportunities for training and building in-country capacity in earthquake and tsunami detection, warning, and alert dissemination. Such training could include, but is not limited to, the development of national Standard Operational Procedures (SOPs) for tsunami warning. | Number of trainings Number of trained personnel | By end of IP, 1 training conducted in each sub-region |
| Actions in Awareness and Response (ICG/PTWS WG 3) |  |  |
| 1. In collaboration, ICG/PTWS WG 2 (Detection, Warning, and Dissemination) and ICG/PTWS WG 3 (Awareness and Response) should work together to promote, organize, and run Exercise Pacific Wave regularly to test communications and improve decision-making from the international to national to local levels. | Exercise Pacific Wave conducted | By end of IP, Exercise Pacific Wave 11 conducted and draft summary report done |
| 2. Provide guidance and/or best practices on national exercises, response and planning, and evacuation strategies | Number of documents | By end of IP, 3 documents done |
| 3. PTWS countries should develop and implement tsunami response plans, including plans for evacuation and communication of information to media and public. | Number of response plans | By end of IP, 50% of MS have response plans |
| 4. PTWS MS (in cooperation with ITIC) should develop appropriate awareness materials, and implement activities and programs to enhance and support the understanding of earthquake and tsunami, and the effective response to tsunami warnings. | Number of activities with materials | By end of IP, all country have conducted 1 awareness activity |

- AREAS OF RESPONSIBILITY (AOR) AND MEMBERSHIP

The PTWS areas of responsibility includes the Pacific Ocean, the Southern Ocean regions of the Pacific and all attached marginal seas, including the Philippine Sea, East China Sea, Yellow Sea, Sea of Okhotsk, Bering Sea, South China Sea, Java Sea, Arafura Sea, Sulawesi Sea, Mindanao Sea, Sulu Sea, Celebes Sea, Bismarck Sea, Solomon Sea, Coral Sea, and Tasman Sea.

The ICG/PTWS presently has 31 Member States:  Australia, Canada, Chile, China, Colombia, Cook Islands, Costa Rica, Democratic People’s Republic of Korea, Ecuador, El Salvador, Fiji, France, Guatemala, Indonesia, Japan, Malaysia, Mexico, New Zealand, Nicaragua, Panama, Papua New Guinea, Peru, Philippines, Republic of Korea, Russian Federation, Samoa, Singapore, Thailand, Tonga, United States of America and Vietnam.  The only Member State of IOC that has not yet become member of PTWS is Solomon Islands.  Several countries are Member States of UNESCO and are not members of IOC neither of PTWS.  These are the Marshall Islands, Micronesia (Federated States of), Nauru, Niue, Palau, Tuvalu and Vanuatu.  According to the current knowledge several of these countries are potentially exposed to the risk of tsunami. They are invited to become a member of the PTWS by becoming a member of UNESCO/IOC.

# ACTION PLAN

Three Central Pillars of PTWS

As outlined in the PTWS Medium Term Strategy (MTS), based on the long term experience of the PTWS and the lessons from the Indian Ocean Tsunami, the immediate central pillars of the PTWS Medium Term Strategy are:

- Risk Assessment and Reduction

- Detection, Warning and Dissemination

- Awareness and Response

Besides these key elements Interoperability of the System is a necessary condition for an efficient warning and for tsunami preparedness while research and scientific projects can be classified as a driving force for accomplishing and continuously improving the three basic elements.

  - Risk Assessment and Reduction

Tsunami hazard assessment consists of several components such as specifying tsunami sources, estimating tsunami effects to the coasts or estimating damages. However, its final aim is to know where the dangerous places are and how strongly a tsunami could affect those areas. Hazard assessment has to be conducted at and by each Member State who best knows the natural and social conditions of its coastal area, and building upon the existing scenarios of Pacific-wide tsunamis to develop local effects of distant tsunamis and add to that the development of regional and local scenarios.

Thus using appropriate historical, bathymetric and topographic data each MS needs to develop tsunami hazard maps for its coastline using harmonized numerical model simulations. Simple and rough estimation, like using elevation data of coastal topography as inundation criterion, can serve a temporary use until more accurate map are developed in the future including through paleotsunami research.

The recommended steps for tsunami hazard assessment in Member States comprise the specification of possible tsunami sources capable of generating tsunamis that affect their own coastal area or the region. Based on these findings local (within 100km of the coastline) and distant source zones should be listed separately as different warning and response procedures are required. Depending on historical data, the distance to the coastline and results from model simulations the hazard risk assessment for each tsunami source will be different.

To develop tsunami hazard maps Member States need to collect information from past tsunami records and/or take into consideration tectonic conditions. Data of past earthquakes and tsunamis are important, but past tsunami databases may lack the severest case(s). So it is advisable to assume the largest scale of geophysically possible cases as well as referring to catalogues and databases of historic tsunamis.

Maximum tsunami height distribution charts of wide areas produced by numerical simulation can be used as guidance for further refined studies where these charts will help to define which the specific areas and retained scenarios are.

Based on the above mentioned historical records, detailed bathymetric and topographic maps and subsequent extensive numerical simulation studies, and any other available means the tsunami threat at each coastline or dangerous area needs to be specified.

Since the works for the above steps includes technical and research capabilities, capacities and skills, it needs support from or cooperation with research communities. To make it relevant and timely a compromise solution should be sought in terms of accuracy in the short term, because it would take long time and large budgets to pursue it due to its continuous improvement.

In the long term, it would be ideal to have MSs’ own available experts who can deal with various technical matters. Such human resources development is essential for the sustainability of the system. It requires training courses, overseas or national opportunities for graduate or postgraduate education and scientific and technical networking.

    - Current Status

Relevant geological subduction zones are shown in Fig. 1, which also identifies several earthquakes of magnitude greater than 8.5 in the last 100 years that have been the source of ocean-wide tsunamis in the Pacific Ocean. This information provides the starting point for any assessment.  However, much more is needed to assess the local threat at a certain coastline.

Figure 1. Global tsunami source zones.  Courtesy LDG-France

Several Member States in the Pacific Rim have been producing tsunami inundation maps of their main ports or coastal cities to help emergency authorities to plan and mitigate the effects of a tsunami.

In the South East Pacific the Servicio Hidrografico y Oceanografico of the Chilean Navy (SHOA) has produced more than 30 tsunami inundation maps for its coastal areas including for Easter Island.  The Direccion de Hidrografia y Navegacion of the Peruvian Navy (DHN) has produced more than 60 inundation maps also available from the Internet. The Instituto Oceanografico of the Ecuadorian Navy (INOCAR) has developed inundation maps for several localities including Esmeralda. Furthermore, the Centro de Contaminacion del Pacifico (CCCP-DIMAR) of the Colombian Navy has produced a tsunami inundation map for the city of Tumaco.  These countries are still in the process of completing the coverage of hazard maps and upgrading the existing inundation maps, including far field simulations and wave propagation of coastal tsunamis toward their coastline including narrow inlets and sounds.

In the South West Pacific, Geoscience Australia has received support from AusAID to partner with the South Pacific Applied Geoscience Commission (SOPAC) to assist Pacific countries in assessing the tsunami hazard faced by nations in this region. The report of this effort provides a probabilistic tsunami hazard assessment (PTHA) to quantify the expected hazard for the SW Pacific nations including American Samoa, Cook Islands, Fiji, Federated States of Micronesia, French Polynesia, Guam, Kiribati, Marshall Islands, Nauru, New Caledonia, Niue, Palau, Papua New Guinea, Samoa, Solomon Islands, Tokelau, Tonga, Tuvalu and Vanuatu. The authors of this report recommend that more detailed studies be undertaken, particularly of the nations with the highest hazard. Those are, in a 2000 years return period, Guam, New Caledonia, Niue, Papua New Guinea, Tonga and Vanuatu.  In particular, future studies should use a higher resolution and more accurate bathymetry for the southwest Pacific islands.

In French Polynesia, a project of tsunami risk assessment and prevention, in the framework of a more global risk project lead by French BRGM (Bureau des Recherches Géologiques et Minières), was performed in 2005 and 2006. In addition to the assessment of regional seismic hazard, the CEA/DASE and LDG/Pamatai were in charge of gathering and synthesizing tsunami data bases (tsunamis having reached French Polynesia, observed tide gauges of events, observed damage) and in a second step to provide numerical constraints to the establishment of PPR (Plans de Prévention des Risques) for exposed bays. Six bays were studied in detail, in the Society Islands, in the Marquesas Islands, and in Tuamotu, while a more regional numerical approach has provided elements to assess a level of hazard along the Polynesian coastlines (i.e. not exposed, moderately exposed, highly exposed).

In recent years, the National Institute of Water and Atmospheric Research (NIWA) has completed several studies of potential coastal inundation from tsunami around the NZ coast., using an advanced hydrodynamic computer model RiCOM (developed by Dr Roy Walters), specifically designed to simulate the propagation and inundation of tsunamis. Combined with high-resolution LiDAR coastal topography, potential inundation at numerous communities from tsunamis of varying sources has been predicted. The sources of the modelled tsunamis were carefully selected as the most-likely worst-case events, and include remote events generated by earthquakes off South America, and local and regional events generated by landslides and earthquakes of varying magnitude in the Hikurangi Trough and the Tonga-Kermadec Trench. Areas of New Zealand modelled to date include communities in Northland and Auckland regions, the Bay of Plenty, Hawkes Bay, Canterbury, Otago and Fiordland.

In Australia several organizations are conducting geologic and tectonic research to form the basis for probabilistic tsunami hazard/risk models. Several organizations are developing tsunami wave propagation modelling capabilities. The Bureau of Meteorology is developing a tsunami wave propagation modelling capability, focusing on real-time monitoring and tsunami warnings.  The University of Queensland is developing numerical models of earthquake and tsunami generation, and tsunami propagation, with emphasis on detailed three-dimensional effects and implications of seismic source rupture characteristics. Geoscience Australia, together with the Australian National University, has developed a 2-dimensional tsunami inundation model that can model tsunami waves in shallow water (< 50 m) and the resulting inundation and run-up onto the coast. The software, ANUGA, has been released as an open source project and as is available for download.  They are also working with the Australian Hydrographic Service and others to develop detailed bathymetry and topography profiles of the Australian coastal environment for input to tsunami inundation modelling.

Japan is by far the most advanced country in terms of the development of tsunami inundation maps.  A range of institutions provide different products including Probabilistic Tsunami Hazard Assessments (PTHA) and specific and detailed assessments to be used by the communities and local authorities.

As the South China Sea is regarded as an area with high possibility of earthquake-generated tsunamis in the coastal areas of China, a plan to enhance China's technical capabilities is ongoing in the eleventh 5-year plan from 2006 to 2010.  The National Marine Environment Forecasting centre (NMEFC) collaborates with other institutes and colleges to conduct research on tsunami generation, inversion of fault mechanism, high precision tsunami and modelling.

After the 26 December 2004 tsunami, the Malaysian Centre for Remote Sensing (MACRES) carried out an inundation mapping and has produced a series of maps showing the areas affected by the tsunami. These maps serve as a useful source for risk assessment. The government of Malaysia through its Inter-Agency Committee on Earthquake and Tsunami Risk Management has appointed the Academy of Sciences Malaysia to carry out a 2-year project to study and assess, inter alia, seismic and tsunami hazard and risk in Malaysia.

In Singapore a two-year study, commissioned by the Meteorological Services Division, National Environment Agency (MSD), to study the possible impacts of tsunami on Singapore was completed in August 2008. During the study, MSD worked with researchers from the local tertiary institutes, namely, the National University of Singapore and the Nanyang Technological University, to assess the possible impact of tsunamis on Singapore and to develop tsunami modelling capabilities. The research study focused on Singapore and considered tsunami sources aligned along the Sunda Trench and Manila Trench. In addition to earthquake-generated tsunamis, a hazard assessment of tsunami-genic submarine landslides in the basins of the South China Sea and the Andaman Sea was also conducted using fine-scale bathymetry data. The tsunami modelling project confirmed that the likely impact of tsunami on Singapore is small.

In Central America, the Instituto Nacional de Estudios Territoriales of Nicaragua (INETER) has been leading the development of tsunami hazard maps in the region, with a tsunami inundation map produced for the area of Masachapa. In Costa Rica the Red Sismologica Nacional (RSN-ICE-UCR) initiated studies for the area of Punta Arenas.  According to these both localities are vulnerable to tsunamis. As well, the Japanese International Cooperation Agency (JICA) working with the Instituto de Estudios Territoriales de El Salvador (SNET) has developed preliminary maps for areas of San Luis Talpa y San Pedro Masahuat. Of the areas under the responsibility of PTWS this regions is clearly under sourced in terms of tsunami hazard studies and requires more effort to cover basic regional and local needs.

Tsunami research is conducted by in the United States by NOAA's Environmental Research Laboratories and by various universities under the direction of the National Science Foundation (NSF).  The World Data Center for Solid Earth Geophysics, including tsunamis (WDC), is operated by NOAA's National Environmental Satellite, Data & Information Service's (NESDIS) National Geophysical Data Center (NGDC).  The US Geological Survey (USGS) is responsible for seismological research and their National Earthquake Information Center (NEIC) assists the TWS through the provision of real-time seismic data and by cooperation and collaboration on other aspects of seismic data collection and analysis.  NOAA’s Tsunami Program has defined in its Strategic Plan 2008–2017 to increase the number of Inundation Forecast Models developed for specific high-risk areas from 26 to 75 by 2013.

In Canada, high-resolution topographic data was collected at Ucluelet using topographic LIDAR. The 2m "bare earth" topographic grid produced using this data was merged with the bathymetric grid to produce a seamless, high-resolution 10m grid so that the effects of inundation can be modelled. This work was done by the University of British Columbia and Spatial Vision Group.  The study (Tsunami Loss Estimation and Emergency Planning for West Coast Communities) was completed in early 2007. The results were presented to the community of Ucluelet to assist them with their emergency management planning. In March 2007 LIDAR data was collected along the coastline of southern Vancouver Island in the vicinity of Victoria, BC from Sombrio Point to Oak Bay. The data has not yet been processed into a digital elevation model.

    - Paleotsunami research and vulnerability studies

Paleotsunami studies in the Pacific area are scarce. The National Institute of Water and Atmospheric Research (NIWA) of New Zealand has developed a paleotsunami (pre-historic) database with at least 35 events. All relevant references are catalogued and are available in hard copy and electronic form. The database is being continually updated. Data from Hawke’s Bay, Otago, Manawatu-Wanganui, and West Coast regions; Taranaki district; and Christchurch city have been collected. Reports for Otago region and Christchurch city have been published, and others are in preparation. These data have been added to the paleotsunami database. GNS Science has revised the historical tsunami database, which now includes 87 events and impact data at over 500 locations, with early historical events continuing to be identified. The database is available via the GeoNet website.

In Australia the James Cook University is conducting field studies of prehistoric tsunami in Australia and South-East Asia. Wollongong University is conducting field studies of prehistoric tsunami in Australia.  Macquarie University and Geoscience Australia are evaluating earthquake sources at the plate boundaries to determine the likelihood of tsunami originating from these sources. Geoscience Australia has conducted an exploratory survey of a portion of the NSW coast in south-eastern Australia to provide input to research on potential landslide sources along the continental margin.

An accomplished risk and hazard assessment includes ideally an assessment of vulnerability. Indeed, a tsunami early warning system aimed to minimize the number of fatalities and injuries should consider at earlier stages the identification of vulnerable groups like children, handicapped and elderly people. In addition to these results, it is likely that tsunamis may provoke fatalities in places which can congregate vast amounts of people such as public markets, churches or cinemas, as well as in the case of those people with permanent or temporary incapacities to move, particularly patients in hospitals.

    - Implementation Actions for Hazard Assessment

The following PTWS Actions to improve Tsunami Hazard Assessment have priority for 2009-2010:

- Upgrade existing tsunami inundation maps in the South East Pacific to include far field tsunamis and hazard maps for oceanic islands.  Complete the coverage for risk areas that fail to have tsunami inundation maps.

- Develop tsunami inundation maps for selected coastal areas of the following South West Pacific countries: Guam, New Caledonia, Niue, Papua New Guinea, Tonga and Vanuatu.

- Complete the coverage of tsunami inundation maps in the area of Central America.

- Provide opportunities for training in tsunami numerical modelling and production of tsunami inundation maps.  Priority should be assigned to trainees from countries located in Central America, South West Pacific and South East Pacific, in the same order.

- Continue developing capabilities and international collaboration for paleotsunami studies in the PTWS AOR.

- Further explore the potential for use and application of vulnerability studies to selected populated coastal cities in risk areas according to the existing inundation maps.

The Working Group in charge of hazard assessment will be requested to contribute to select priority areas and suggest appropriate methodologies as needed.  Funding for training will be prioritized by the Secretariat both from extra budgetary sources as well as from regular programme budget. Linkages will be established with IOC programmes (i.e. Ocean Mapping, IODE, GOOS) and with partner organizations (i.e. UNDP, SOPAC, CPPS) that could contribute to this central pillar.

Performance indicators for these actions should be elaborated and assessed against benchmarks, both developed by the PTWS Secretariat and reported to regular ICG/PTWS meetings.

  - Detection, Warning and Dissemination

The Pacific is the world’s largest ocean with potential tsunami sources mainly located in the so-called Pacific Ring of Fire extending over 40,000 km horseshoe-shaped along the ocean’s fringes.  It is associated with a nearly continuous series of oceanic trenches, volcanic arcs, and volcanic belts and/or plate tectonics. Given this wide-spread extension it is appropriate to consider it in several geographical scales when dealing with tsunami warning systems. Thus the tsunami warning system in the Pacific is divided into different scales i) national or local ii) regional and iii) ocean wide warnings.

    - Local (or National) warning

Local or national warning systems are the most crucial part in the entire end-to-end system for both local and distant tsunamis, due to the inalienable and sovereign national responsibility of informing people at risk and urge or order immediate evacuation.

The successful establishment of (some fully fledged) National Tsunami Warning Centres (NTWC) is within the responsibility of MSs and a prerequisite for a regional or Ocean wide system. In any case each nation has to establish an appropriate emergency response mechanism on a 24/7 basis among concerned national agencies. This includes optimized procedure for all steps; from issuing warnings to evacuation of coastlines as well as continuous practices through full scale evacuation exercises and drills.

For local tsunamis, which occur just near the coast of a particular country, there is usually a very short time until the tsunami hits the coast. Therefore, local or national warning system should initiate emergency action on their own without waiting for information from overseas organizations. For distant tsunamis, local and national systems securely receive information from international centres, evaluate the effect on domestic coastlines and decide to issue national warnings.

    - Regional warning

For areas and coastlines, encompassing several countries, which are threatened by one or more tsunami source zones, building a regional TWS with the capability to alert all MSs concerned within that sub-region is a very cost-effective way facing the common threat. Obviously close cooperation among neighbouring MSs is essential for the set-up and operation. In some cases, such a regional systems may be considered as a wide-spread local system mandated to warn several national disaster management agencies at a time (e.g.. system in the Southwest Pacific region where proper detection of earthquakes is difficult in a single country due to sparse distribution of small islands).

The Northwest Pacific Tsunami Advisory Center (NWPTAC) offers a regional warning service to the PTWS formally as from 1 February 2006.  The NWPTAC is operated by the Japan Meteorological Agency (JMA) and provides tsunami advisories for large earthquakes occurring in the northwest and a portion of the southwest Pacific.  The advisories are issued to nations in the region who have designated a 7x24 Tsunami Focal Point (NTWFP)for the receipt of official tsunami information.  The Northwest Pacific Tsunami Advisory (NWPTA) is issued in conjunction with the international tsunami bulletins of the Pacific Tsunami Warning Center (PTWC), and consists of earthquake information, tsunami-genic potential, estimated wave heights and arrival times of tsunami, and observations of tsunami.

The ICG/ITSU requested, at its 20th session, the NWPTAC and the PTWC to provide the interim tsunami advisory service for the South China Sea region (SCS).  In response to the request, JMA upgraded its system and started the service for the SCS in April 2006.  The new service was reported to the 39th session of the IOC Executive Council held in June 2006 and the NWPTAC and the PTWC were requested to continue the interim SCS service at least until the 22nd session of the ICG/PTWS in September 2007.  The ICG/PTWS requested, at its 22nd session, to furthermore continue the interim service and submitted to the IOC Executive Council a Recommendation that requests the formal authorization of the service.  In response to the Recommendation, the IOC Executive Council, at its 41st session in 2008, adopted a Resolution which endorses the interim service for the South China Sea provided by the PTWC, the WC/ATWC and the NWPTAC. Figure 2 shows the Area of Responsibility for the interim service for the South China Sea including the forecast points.

Figure 2. Forecast Points (black dots) in the South China Sea

Member States of the South East Pacific region have opted or a different solution which is to boost sharing real-time seismic and sea level data among MSs within the region and develop communications protocols for tsunami regional events.

    - Ocean-wide warning

The Ocean-wide system deals with tsunamis capable of expanding in a wide area of the Pacific Ocean, affecting a number of countries. This system uses global observational networks of seismic and sea level data, and also requires prompt and reliable communication means to deliver tsunami alert messages to scattered countries around the Pacific Ocean. This tsunami alert information has the role of triggering the national warning procedures in each MS for ocean-wide tsunamis. This part of PTWS is operational since more than 40 years and actually serviced by the three current International Tsunami Centers, PTWC, WCATWC and NWPTAC.

The USA and Japan continue their operational services in close cooperation for providing consistent and effective Warning/Advisory Service. Any further improvement of PTWS will be constructed on the basis of the present system and service. Nevertheless i) providing tsunami height estimations, ii) improving tsunami estimation accuracy and iii) improving earthquake determination (location, depth and M) accuracy are the discussed next targets.

Basically state-of-the-art technologies need to be carefully assessed before replacing operationally robust technologies. It is essential to evaluate the newest, promising technologies from the viewpoints of not only effectiveness or attractive prospects but also operational reliability and robustness, when considering introducing them into the warning system.

    - Seismic and sea level instrumentation networks

Any tsunami warnings or tsunami alert messages from Ocean-wide or regional tsunami warning centers (RTWC) rely on a dense network of seismic and sea-level instrumentation. The existing PTWS instrumentation networks so far are mainly designed for large scale (distant) tsunamis with the ability to warn far-field coastlines while only a very few MS like Japan do have dense enough instrumentation networks and thus the ability to warn their population in due time of also local tsunami events. Therefore one of the most imminent and urgent needs of the PTWS is the upgrading and densification of observational networks for seismic and sea level data including improved online communication system(s) to rapidly collect these data. Additionally capabilities to analyze those data, evaluate tsunami effects and issue tsunami warnings through improved communication networks for delivering warnings and information needs to be reinforced.

The improvement of seismic and sea level observation networks needs to be implemented by all MS based on the agreed upgrading recommended by the PTWS working groups on seismic and sea-level instrumentation. This process requires considerable funding and human resources and thus it should build upon and make efficient use of existing support mechanisms and international networks such as CTBTO, FDSN and IRIS for seismic monitoring and IOC/GLOSS for sea level monitoring.

      - Sea level instrumentation networks

The ICG/PTWS Member States operate, directly or indirectly, more than 375 sea level stations capable of measuring tides, storm surges and tsunamis. Many of these stations are capable of providing data in real-time or near real-time for use in tsunami detection and

Figure 3.  Sea level gauges in the Pacific and adjacent regions that are used by PTWC for tsunami wave detection and evaluation.  Red dots are coastal gauges with transmission intervals ranging from 6 minutes to an hour.  Magenta dots are deep-ocean DART gauges, 32 operated by the U.S., 3 by Australia, and 1 by Chile.  Green dots (Hawaii and New Zealand) are coastal gauges that transmit continuously in real time.  Yellow dots (Hawaii) are dial-up gauges.  Not all gauges are currently operational, with outages producing notable gaps in the northwest Pacific and along Central and northern South America.

warning.  At the heart of this network of “tsunami” stations are 74 GLOSS “fast delivery” coastal sea level stations. These stations provide data at transmission intervals ranging from 3

minutes and in some cases up to to 3 hours utilizing USA GOES and Japan GMS satellites that make up part of the WMO’s Global Telecommunications System (GTS). The data is available to the Pacific Tsunami Warning Center (PTWC), as well as other regional and national centres that have downlinks to the GTS. Most of the stations on the GTS are also available at the IOC Sea Level Station Monitoring Facility web-site :

www.ioc-sealevelmonitoring.org

In May 2007 approximately half of the coastal sea level stations available by this mean have transmission rates of 1 hour or more. While these transmissions are “adequate” for basin-wide events, they are of limited or no use for regional or local tsunami events. Many of the other stations (mainly USA NOS), transmit on GOES E-W with a 6-minute transmission interval. The ICG/PTWS has recommended that the standard for all stations used for tsunami warning and detection should have data transmission intervals of five (5) minutes or less.  In deciding upon the priority for stations for upgrade, the ICG/PTWS recommends those stations within 1-hour tsunami travel time of tsunami source zones to be the highest priority (Figure 4). The ICG/PTWS is working with GLOSS and USA NESDIS, who oversees the GOES satellite services, to increase the service bandwidth available and thus allow the number of stations that can be transmitted over existing channels to increase.

Within the remaining network of GLOSS “fast delivery” sea level stations, a preliminary list of priority stations for upgrade has been identified and is being validated (Table 1 at the end of this document). Also included are other stations presently being received at the PTWC by GTS at transmission intervals greater than 10 minutes. With the exception of Australia, the NE Pacific and some islands in the north Pacific, all areas are in need of more frequent data transmissions.

The PTWS Sea Level Network for tsunami monitoring is comprised of nationally-supported contributions of data in real or near-real time through the GTS, in addition to stations maintained and operated by the PTWC and University of Hawaii Sea Level Center.  As such, upgrades will be dependent on initiatives and support from a number of institutions.  For example, Australia (through AUSAid) is working with many of the Pacific Island countries in the South Pacific Region to conduct a tsunami capacity assessment. The results of those capacity assessments should help to confirm the selections in that region or identify other priority stations for upgrade.

An important consideration for upgrade strategies will be stations located near major subduction zones or at strategic mid-ocean locations. Figure 4 shows all stations (GLOSS and other) presently received by the PTWC through the GTS. Stations situated within 1-hour tsunami travel time (approximate) of a major subduction zone are in the areas marked in blue.

Figure 4.  GLOSS and other sea level station data received by the PTWC. Darker blue shaded region shows areas within 1-hr tsunami travel time of tsunami source zones. Stations within this area should receive higher priority for upgrade of the transmission frequency to 5-min intervals.

More timely transmission of data is only one component of an effective contributing station. It is also important to identify stations which have a history of reliable operation and that are presently collecting 1-minute data, or are capable of collecting data at 1-minute intervals.

It is important to identify additional (new) priority stations in areas where coverage is not yet adequate. The ICG/PTWS will work with GLOSS to identify stations which are not presently part of the GLOSS network, but which would make valuable contributions to GLOSS. It is critically important that any new or upgraded stations be sustainable, and a commitment to both ICG/PTWS and GLOSS will help Member States justify that commitment. The high quality of GLOSS data worldwide is of great benefit to the regional Tsunami Warning Systems (TWS), and a regional TWS’s requirement for data that is timely and of high quality is of benefit to GLOSS.

In Table 1, 88 potential upgrade candidates are identified. Within this list of candidate stations are 59 stations located close to major subduction zones. Twenty five of these stations are GLOSS stations. Also identified are 29 additional GLOSS stations which are not presently transmitting data via GTS – 22 of these stations are located in the western Pacific region and 7 in the eastern Pacific region.

      - Seismic instrumentation networks

Data from seismic stations around the Pacific, primarily broadband stations, are the basis for the preliminary earthquake epicentres and magnitudes determined by the TWC.  Most of these data are provided the IRIS Global Seismic Network (GSN).  Data are sent in real time in the form of continuous digital waveforms using a variety of communications methods and circuits.  The current network (September 2010) of the GSN is shown by Figure 5.

Figure 5.  Seismic monitoring network of the IRIS Global Seismic Network (GSN)

PTWC uses a dense array of stations for tsunami monitoring purposes, both from GSN and other US national network stations.  The WC/ATWC and NWPTAC use almost the same network for the determination of the hypocenter and magnitude.

The global network of the International Monitoring System (IMS) of the Comprehensive Nuclear-Test-Ban Treaty Organization (CTBTO), once completed, will consist of 321 monitoring facilities of four different technologies: hydroacoustic, seismic, infrasonic, and radionuclide. As of today, about 65% of the installations are completed and contribute data to the products issued by the International Data Centre (IDC) of the CTBTO. In order to accomplish the task to reliably collect evidence for any potential nuclear test explosion anywhere on the planet, all stations are required to perform to very high data availability requirements (at least 98% data availability over a 12-month period). This high reliability coupled with a reduced data distribution time (30 seconds instead of 100-180 seconds) makes the CTBTO/IMS seismic data very attractive for tsunami monitoring purposes.  For this reason, the Preparatory Commission (PrepCom) for the Comprehensive Test Ban Treaty Organization (CTBTO) in Vienna decided to explore options for releasing data from its International Monitoring System (IMS) to tsunami warning organizations. On a trial basis, the Provisional Technical Secretariat of the CTBTO was given the mandate to share data from its seismic and hydroacoustic stations immediately with any tsunami warning organization recognized by the United Nations Educational, Scientific and Cultural Organization (UNESCO).  The use of CTBTO/IMS data has greatly improved the capabilities of the PTWS warning centers.

Several initiatives are in the process to cover monitoring gaps in the South East Pacific and in the South West Pacific.  For example, the Japanese International Cooperation Agency (JICA) is providing technical assistance for Fiji and Tonga to construct and operate earthquake observation networks in cooperation with the National Research Institute for Earth Sciences and Disaster Prevention (NIED) and other organizations. The project was started in November 2007 to provide equipments of satellite telemetry broadband seismic networks, to dispatch experts of earthquake observation and seismology, and to conduct training in Japan and in the relevant countries.  The broadband seismic networks can be a part of local tsunami warning systems of the two countries and also have a potential to contribute to the tsunami warning systems in the Pacific.

    - Communication Tests and Tsunami Warning Focal Points (TWFP)

To confirm the communications status on distributing the NWPTAs, the NWPTAC carried out the latest communications test on 22 January 2009.  The results indicate that most of the recipients had received the test message successfully.  They reported back that they received the test message within a few minutes after the NWPTAC transmitted the message.  It shows that the communications between the NWPTAC and the northwestern region countries are in a good condition.  However the NWPTAC did not receive an acknowledgement from some recipients.  Without an acknowledgement, it is impossible to verify the condition of the recipient including the status of the communication route. In order to ensure the solid communications for receiving NWPTAs, all recipients are required to send the acknowledgement during the communications test. Currently the NWPTAC sends its messages to 28 fax numbers and 35 e-mail addresses. Since starting its operations in March 2005, the NWPTAC has received a number of requests to add recipient fax numbers or e-mail addresses, while there was no withdrawal of unnecessary/disposed numbers or addresses.  Increase in the number of fax numbers and e-mail addresses may cause a serious delay in the transmission of messages to recipients.  Although no trouble has arisen so far, the recipients will be requested to review their presently registered fax numbers and e-mail addresses and adhere strictly to the rules governing the nomination of Tsunami Warning Focal Points (TWFP) as described in the Operational Users Guide for the Pacific Tsunami Warning and Mitigation System (PTWS) (IOC Technical Series, 87).

While the precise production and definition of a tsunami warning requires specific capabilities, the delivery of warnings to the population is usually provided through other mechanisms by mandated agencies (Interior, Cabinet, Civil Defence, Hydrometeorological and Weather Services). Early involvement of these bodies in the national tasks of PTWS may help save time and money.  It would be advisable that a combination of technical agencies (i.e. geophysical or oceanographic institutions) and disaster management agencies develop together mechanisms and processes for tsunami warning and response at the national level through commonly agreed and accepted Standard Operational Procedures (SOPs). The UNESCO/IOC International Tsunami Information Center (ITIC) has been involved in SOPs projects for the Indian Ocean (funded by UNESCAP and UNDP) and will most probably be involved in SOP training for the Caribbean region (funded by USAid).  The Member States of the PTWS should benefit of these experiences and reinforce and expand their response procedures.

    - Implementation Actions for Warning

The following PTWS Actions on sea level monitoring have priority:

- Update the list of candidate stations for upgrading and provide information on this initiative at GLOSS-GE meetings (Table 1).  The main participants in the preparation of this initial list were PTWC staff and UHSLC (GLOSS).

- ICG/PTWS Working Group 2 on Sea-level Measurements, Data Collection and Exchange will continue to refine and validate this list and provide this information for guidance in the development of the ICG/PTWS Implementation Plan.

- ICG/PTWS Member States will be informed and asked to provide input on priority, contribution of resources, and long-term maintenance commitments to ensure sustainability.

Considering that the US Tsunami Program may receive some additional funding over the next 3 years to accelerate its progress, the following two activities can be facilitated by these additional resources.

- Modernization and convergence of the IT infrastructures of PTWC and WCATWC.  Associated with this modernization effort will be the convergence and unification of the PTWC and WCATWC web sites and the development of a uniform set of graphical products that incorporate more detailed tsunami forecasting information.

- Enhanced support for Pacific coastal sea level gauges outside the US.  PTWC operates or helps to operate a number of coastal sea level gauges located outside the US that fill gaps in coverage near tsunami source zones.  They include sites in Central and South America, the northwest Pacific, the far west Pacific, and some of the Pacific Islands.  Restoring and/or upgrading these gauges will help ensure the speed, accuracy, reliability, and comprehensiveness of PTWS warning operations.

The following PTWS Actions for communications have priority:

- The Secretariat shall secure by end of May 2009 that all PTWS MS have formally defined their TWFPs and have updated their contact details, for onward transmission to PTWC and NPTWAC.

- Member States and the Secretariat with the active support of ITIC will develop training activities and hands-on workshops towards a wide adoption of Standard Operational Procedures (SOPs) for tsunami warning. Funding from international agencies and regional cooperation bodies will be sought towards these activities.  All Member States are concerned.

Performance indicators for these actions should be elaborated and assessed against benchmarks, both developed by the PTWS Secretariat and reported to regular ICG/PTWS meetings.

  - Awareness and Response

Disaster Preparedness is to be promoted in those very places vulnerable to the effects of tsunami, and hence it is basically to be taken up by each MS. It encompasses in a broader definition all activities that help to "prepare" for a tsunami including hazard assessment, monitoring and warning services.  However, and in the context of tsunami, it has been most frequently associated with population preparedness and training and public awareness activities.  There are two levels for it, one is the governmental level in that they issue warning for evacuation, and the other is individual people’s level in that they receive warning and take their own evacuating action or response.

    - Culturally adapted manuals, brochures and posters

Besides preparedness and awareness raising programs for people in endangered areas, building evacuation maps for residents and capacity building for governmental officials are key targets for national authorities.

Translating existing good educational materials into local languages and delivering these materials to the people is one of the best ways for disaster prevention education. The UNESCO/IOC International Tsunami Information Center (ITIC) has been for a long time the repository centre for all tsunami awareness and preparedness materials produced in all languages.  In recent years the rapidly growing interest on these matters has increased the number of existing publications and materials. MS in cooperation with ITIC and other relevant international organizations should continue adapting educational materials and translating these into local languages.

    - Drills and Exercises for Tsunami Warning

Full scale evacuation exercises and drills should be considered as reliable preparedness tools to test both warning systems and evacuation plans. It also helps to improve awareness and local governments’ and population involvement.

The first end-to-end Pacific-wide tsunami exercise, entitled Exercise Pacific Wave (EPW06) 2006, on 16-17 May 2006 was a milestone for PTWS.  Altogether, 44 countries participated, including 29 of the then 30 ICG/PTWS Member States.  Five countries also carried out public evacuations, thus exercising procedures down to the very “last mile.”  Opportunities for regional cross-learning and best-practice sharing were provided to enable several countries to participate as observers to the end-to-end communications exercise and community evacuation conducted in the Philippines.  The exercise provided an opportunity for Pacific countries to exercise their operational lines of communications, review their tsunami response procedures, and at the same time, promote emergency and tsunami preparedness.  Each country participated in at least one of two tsunami scenarios initiated over the 16-17 May 2006 period.   One scenario originated from the eastern Pacific off the central Chilean coast (16 May).  A second scenario originated from the western Pacific, north of the Philippines (17 May).An Exercise Pacific Wave ’06 Summary Report is available as document IOC/INF 1244.

A second end-to-end Pacific-wide tsunami exercise, entitled Exercise Pacific Wave (EPW08) 2008, was held on 28–30 October 2008 with similar commitments and results.

These exercises can be conducted at various scales of magnitude and sophistication. The following are types of exercises that can be conducted:

Orientation Exercise (Seminar): An Orientation Exercise lays the groundwork for a comprehensive exercise program. It is a planned event, developed to bring together individuals and officials with a role or interest in multi-hazard response planning, problem solving, development of standard operational procedures (SOPs), and resource integration and coordination. An Orientation Exercise will have a specific goal and written objectives and result in an agreed upon Plan of Action.

Drill:  The Drill is a planned activity that tests, develops, and/or maintains skills in a single or limited emergency response procedure.  Drills generally involve operational response of single departments or agencies, organizations, or facilities, but may be a subset of full-scale exercises.  Drills can involve internal notifications and/or filed activities. Limited evacuation may or may not be conducted, such as within a school, pilot hotel, or village.

Tabletop Exercise:  The Tabletop Exercise is a planned activity in which local officials, key staff, and organizations with disaster management responsibilities are presented with simulated emergency situations.  It is usually informal, in a conference room environment, and is designed to elicit constructive discussion from the participants to assess plans, policies, and procedures.  Participants will examine and attempt to resolve problems, based on plans and procedures, if they exist.  Individuals are encouraged to discuss decisions in depth based on their organization’s Standard Operating Procedures (SOPs) with emphasis on slow-paced problem solving, rather than rapid, real time decision-making. An Exercise Controller (moderator) introduces a simulated tsunami scenario to participants via written message, simulated telephone or radio call, or by other means.  Exercise problems and activities (injects) are further introduced. Participants conduct group discussions, and resolution is generally agreed upon, and then summarized by a group leader.  A Tabletop Exercise should have specific goals, objectives, and a scenario narrative.   See Appendix V for a summary on Tabletop Exercises.

Functional Exercise:  A Functional Exercise is a planned activity designed to test and evaluate individual capacities, multiple activities within a function, or interdependent groups of functions among various agencies.  It is based on a simulation of a realistic emergency situation that includes a description of the situation (narrative) with communications between players and simulators.  The Functional Exercise gives the players (decision-makers) a fully simulated experience of being in a major disaster event.  It should take place at the appropriate coordination location (i.e. warning and emergency operations centers, command center or post, master control center, etc.) and activate all the appropriate members designated by the plan. For a tsunami exercise, organizations should test their SOPs using real time simulation tsunami bulletins. Both internal and external agencies (government, private sector, and volunteer agencies) should be involved.  It requires players, controllers, simulators, and evaluators.  Message traffic will be simulated and inserted by the control teamfor player response/actions, under real time constraints. It may or may not include public evacuations.  A Functional Exercise should have specific goals, objectives, and a scenario narrative.

Full-scale Exercise:  A Full-scale Exercise is the culmination of a progressive exercise program that has grown with the capacity of the community to conduct exercises.  A Full-Scale exercise is a planned activity in a “challenging” environment that encompasses a majority of the tsunami warning and emergency management functions, and involves multiple layers of government (national, provincial, local).  This type of exercise involves the actual mobilization and deployment of the appropriate personnel and resources needed to demonstrate operational capabilities.  Emergency  Operations Centres EOCs and other local command centres are required to be activated. It tests all aspects of emergency response, and should demonstrate interagency cooperation.  A Full-scale exercise is the largest, costliest and most complex exercise type.  It may or may not include public evacuations.

Member States of the PTWS are strongly encouraged to develop the above exercises, progressively going from the simplest to the full scale.  As well, Member States are invited to plan for and participate actively in the future (EPW11)

    - Implementation Actions for Preparedness

The following PTWS Actions on preparedness have priority:

- Organize and run the Exercise Pacific Wave 2011 (EPW11) increasing the number of participating countries as well as the total number of full scale exercises happening at the same time.

- Enhance ITIC's capabilities to collect, catalogue, adapt, reproduce and distribute public awareness and educational materials for tsunami preparedness.  Electronic means should be prioritized when necessary and partner organizations will be solicited to contribute funding towards these actions.

Performance indicators for these actions should be elaborated and assessed against benchmarks, both developed by the PTWS Secretariat and reported to regular ICG/PTWS meetings.

  - Interoperability

Regarding PTWS, interoperability has two aspects. One is standard setting and collaboration among the four ICGs on regional TWS and the other is addressing tsunami and other hazards related to sea-level through TOWS-WG and thus ensuring coordination with relevant IOC bodies like GLOSS and ICAM but also other UN agencies and bodies concerned. The basic idea for both is to make the best use of limited resources such as experts, infrastructure, or funding efficiently. Such interoperability should be paid attention when the three central pillars described above are considered, especially when developing observational systems and establishing national emergency response systems.

In doing so the PTWS together with all ICGs needs to examine and extract common characteristic issues and items for every technical matter. The PTWS MTS 2009-2013 and the PTWS Implementation Plan will be provided for discussion in the TOWS-WG while the current status, successes and failures of each ICG should be shared among all the four ICGs.

  - Research

Utilizing scientific investigation results of characteristics of tsunami phenomenon as well as introducing advanced technologies developed in other technical fields such as communication technology is fundamental for improving tsunami disaster mitigation measures. In that regard, research plays contributes to the three central pillars of the MTS.

There are many new research programs and technologies being conducted and developed day by day. Since they pursue the leading edge science, some of them provide interesting and relevant results in theory, but they need to be validated in an experimental stage in order to be put into practical use. Therefore ICG/PTWS through its working groups has to pre-assess new research results or technologies from various viewpoints such as relevance, effectiveness, efficiency, robustness, maintenance easiness and sustainability before officially introducing them into operational systems.

However, it would not work so effectively only with the Group’s resources, so that ICG/PTWS needs to promote closer cooperation with relevant research communities. ICG/PTWS also should take the role of requesting research communities to conduct or develop research or technology necessary for improving tsunami warning and mitigation system and contribute to solve problems we find through our actual system operations or various other activities.

A Local tsunami is "a tsunami from a nearby source which destructive effects are confined to coasts within 100 km of the source.  A local tsunami is usually generated by an earthquake, but can also be caused by as landslide or a pyroclastic flow from a volcanic eruption" (UNESCO/IOC Tsunami Glossary)

For example, in May 2008, a Regional SIFT/MOST Tsunami Modeling Course was held in Valparaiso, Chile, with the participation of Perú, Ecuador, Colombia, Chile and French Guyana tsunami specialists.  Also, Philippines hosted in November 2005 a training workshop for tsunami modelling attended by 12 countries from the Indian & Pacific Oceans.

http://www.shoa.cl/citsu

http://www.dhn.mil.pe/app/menu/tsunami/cartastsunamis

http://www.inocar.mil.ec/links.php?C=6&S=4&SbS=0&idC=5

Thomas, C. and Burbidge, D. 2009. A Probabilistic Tsunami Hazard Assessment of the Southwest Pacific Nations.  Geoscience Australia Professional Opinion. No.2009/02

https://sourceforge.net/projects/anuga/

http://www.snet.gob.sv/ver/oceanografia