## Slide 1
Agenda 4.2
PTWS Exercise Task Team
ICG/PTWS-XXIV
Beijing, China , 24-27 May 2011
Jo Guard, MDCEM, NZ
Laura Kong, ITIC
Notes: <number>

## Slide 2: PTWS Exercise Task Team – Terms of Reference
(i) Review the PACWAVE08 evaluation report
(ii) Identify lessons learned from PACWAVE08
(iii) Design and carry out a third end-to-end
Pacific-wide exercise
Members:
PTWC, JMA NWPTAC, France, Indonesia, New Zealand (GNS, MCDEM), Nicaragua, Papua New Guinea Philippines, Russian Federation, Southeast Pacific representative (TBD?), PTWS Secretariat

## Slide 3: PacWave08 Lessons Learned for PacWave11 (1/4)
Tsunami Warning Focal Point contact data
  Issue: TWFP contact information incorrect
  => Countries regularly review / confirm to IOC
Conduct exercises in real time
  Issue: Positive in their feedback for real time
  => Regular Pacific-wide exercises to be in real time
Exercise announcements
  Issue: Insufficient time to prepare
  => IOC officially announce 6 months / distribute documents 3 months prior

## Slide 4: PacWave08 Lessons Learned for PacWave11 (2/4)
Local community preparedness
  Issue: Not generally known how successful locally (timely alert and actual evacuation)
  Increase emphasis on local community-based preparedness, training, and “last mile” exercises
Tsunami plans and standard operating procedures
  Issue: Countries did not assemble management group during exercise (but would in a real event). Unclear how many countries pre-determined tsunami plans.
  For fast tsunami response, need end-to-end SOPs. PTWS WG 3 to survey; if training priority, incl training budget in annual natl budget request.

## Slide 5: PacWave08 Lessons Learned for PacWave11 (3/4)
Warning systems
  Issue: Communication to local jurisdictions insufficient for immediate response of coastal communities.
  Conduct feasibility study to identify and evaluate relevant warning systems. Australia (AusAID) PIC Tsunami Capacity Assessments (2009) and PTWS WG 3 survey providing input. PTWS Emergency Communications TT assist in identifying technologies available.

## Slide 6: PacWave08 Lessons Learned for PacWave11 (4/4)
Post-exercise evaluation / Regional Recommendations in context of PTWS Medium Term Strategy
  Issues 1: Large number of questions unanswered so difficult to draw conclusions as part of evaluation process, e.g., regional (PTWS) common priorities of action too specific / did not address PTWS MTS
  => Simpler evaluation questionnaire / electronic online.
  => How to Plan, Conduct, and Evaluate Tsunami Exercises guideline (July 2011, also TOWS Inter-ICG TT)
  => Evaluation directly correlate to - measure PTWS MTS

## Slide 7: Tsunami Wave Exercises: Two Stages
<number>
TWCs
Member
State
Member
State
Member
State
Member
State
Public
Notification
Public
Notification
Public
Notification
Public
Notification
Stage 1
Stage 2
Notes: Animated slide. Click to start. Click after "TWCs" appears. Click again after "Stage 1" appear.
<number>

## Slide 8: PacWave11 – Date and Objective 1
IOC Circular Letter 2390 issued 13 May 2011
  9-10 Nov 2011 - multi-scenario local / regional tsunami; during APEC offering high visibility
  Nominate PacWave11 focal point by 10 June 2011.
Objectives
1. To validate understanding and use of PTWS Experimental Products. Proposed to be tested in PacWave11 through 2013
  Utilise PTWC experimental products, incl forecast models /science info => timely hazard assessment.
  Validate advice issuance from PTWC JMA/NWPTAC
  Validate advice receipt by Pacific country TWFPs.

## Slide 9: PacWave11 – Objective 2
Objective 2.
To validate readiness for local/regional source tsunami
  Improve operational readiness (ensure appropriate tools / response plan(s), incl public education
  Conduct pre-exercise public education on response
  Validate dissemination of NTWC in-country agencies.
  Validate decision-making on warnings / evacuations.
  Validate methods to notify and instruct public.
  Assess elapsed time until public notified
  Validate public information material – Useable/actionable, clear, concise and timely.

## Slide 10: PacWave11 - Scenarios
The scenarios
  Kamchatka (Kuril-Kamchatka Trench)
  Ryukyu Islands (Nansei-Shoto Trench)
  Philippines - South China Sea (Manila Trench)
  Philippines - Pacific Ocean (Philippines Trench)
  Vanuatu (New Hebrides Trench)
  Northern Chile (Peru-Chile Trench)
  Ecuador (Colombia – Ecuador Trench)
  Central America (Middle America Trench)
  Aleutian Islands (Aleutian Trench)

## Slide 11: PacWave11 Scenarios – Example Preliminary Forecast Models (RIFT)

## Slide 12: PacWave11 – Conduct: Start, Messages, Guidance
Time of Event:
  SW Pacific requested during the day.
  Other regions provide input
International TWC Messages
  Only 1st Exercise Start message
  All available on secure web site (save money)
Exercise Manual - available 9 August with details
How to Plan, Conduct, and Evaluate Tsunami Exercise – available July 2011 – use for training and briefings

## Slide 13: Conduct – Manual and Guidance
Exercise Manual – available 9 August with details
How to Plan, Conduct, and Evaluate Tsunami Exercise available July 2011 use for training and briefings

## Slide 14: Conduct – Evaluation, TOWS, Training
Post-Exercise Evaluation
  Focus on plans, policies, procedures, assessment capabilities, communication, resources and inter-agency/inter-jurisdictional relationships
  Aligned with PTWS MTS and its activities
Consistency Globally for Exercise
  IOWave11 – same methodology and questionnaire
  Next CaribeEWS?
PacWave11 briefings and training
  On request – possible partnered trainings
  ITP-Hawaii 2011 (22 Aug -2 Sept) – IOC CL early June

## Slide 15: Questions - Feedback

## Slide 16
Laura Kong
Director
International Tsunami Information Center
Thank You
ICG/PTWS-XXIV
Beijing, China , 24-27 May 2011
Notes: <number>